## Category Clarification
Category | Description
Change Request | New Change Requested on the approved scope and needs development
Missing Requirement | Requirement that was mentioned in the approved scope but wasn’t delivered
Feedback needed from ICIEC | Clarifications or information need to be provided by ICIEC, however upon the feedback, the category might be changed or Dropped.
Feedback needed from ESKADENIA | Verification or clarification needed from ESKADENIA
Enhancement | It’s a change requested but can be done and needs minimum development effort by the team
Setup Configuration | If minor update required on the defined setup
Agent Portal Gap Verification Sessions Results
Category | Updated Number of Points | Old Number of Points
Change Request | 3 | 7
Missing Requirement | 0 | 0
Feedback needed from ICIEC | 0 | 1
Feedback needed from ESKADENIA | 0 | 0
Enhancement | 7 | 2
Setup Configuration | 2 | 2
Total | 12 | 12

## Credit AP Gap Verification Log
# | Session Date | Module | Item | Category | Status | Priority from ESKADENIA perspective | Priority from ICIEC perspective | Remarks - ESKADENIA | Remarks - ICIEC
1 | 2020-04-01 | Agents Portal | Submissions on the portal will result directly to policies reflected at Credit Insurance along with all relevant details. | Setup Configuration | Pending | High | High
2 | 2020-04-01 | Agents Portal | Reference numbers (policies, buyers and approvals) shall be captured and displayed in order to match between ICIEC and Credendo/Coface references. | Enhancement | Pending | Medium | High |  | For all Fronting
3 | 2020-04-01 | Agents Portal | Specification of the channel through which the policy has been acquired along with broker identification, if any. | Enhancement | Pending | High | High | Brokers registered in ICIEC's database will be available under this option.
4 | 2020-04-01 | Agents Portal | Pricing details have to be filled on the portal as ICIEC will follow the pricing of Coface and Credendo. | Enhancement | Pending | High | High
5 | 2020-04-01 | Agents Portal | Validation implementation to control that no claim payment shall take place unless Coface/Credendo have paid their respective portion. | Enhancement | Pending | Medium | High |  | The validation should be applied on optional basis and in accordance with the agreement between ICIEC and the Agents (Credendo, Coface, etc.)
6 | 2020-04-01 | Agents Portal | “Claim Submission”, additional field is required to capture more details along with the possibility to upload documents (attachments). | Setup Configuration | Pending | Low | Medium
7 | 2020-04-01 | Agents Portal | “Claim Submission”, expenses addition with the option to specify whether they will be paid by the policyholder or reimbursed to them. | Enhancement | Pending | Medium | Medium |  | Raised during Business requirements Gathering
8 | 2020-04-01 | Agents Portal | Possibility to bulk import policies, buyers and approvals through pre-defined excel templates to facilitate and fasten the process of data capturing. | Change Request | Pending | High | High | Policy import option shall be discarded. | Raised during Business requirements Gathering
9 | 2020-04-12 | Agents Portal | Feedback is required from ICIEC on the treatment of commission regarding the excess of minimum of premium versus the monthly declarations. | Enhancement | Pending | Low | High | Reference to the call held on 05-05-2020, it was agreed that we shall always pay commission on the excess of MoP.
10 | 2020-04-12 | Agents Portal | Possibility to perform reconciliation and manually adjust the figures and amounts before posting to the Financial entity to consider Coface and ICIEC’s shares according to Sharia compliance. | Enhancement | Pending | Low | High | Reference to the call held on 05-05-2020, it was agreed that no manual adjustment will take place. When posting (generating) MoP invoice for direct business, it should impact a control account. Upon monthly declarations invoicing, debit MoP and credit Revenue until MoP is fully utilized while the excess shall be treated as regular premium invoicing. Example, MoP is 100K, invoiced declarations for a period are 95K. For a certain month, if the submitted declarations' premium is 10K, then 5K shall be deducted from the MoP while the remaining 5K shall be issued as a normal premium invoice. At the end of the policy period, if the MoP is not fully utilized, then reconciliation occurs (Credit Gap - Point #154) with the possibility to (Revolve, Refund or Transfer to Waqf).
11 | 2020-04-12 | Agents Portal | No claim bonus consideration for Credendo policies whereby at the end of the policy year, if no claim, then bonus might be provided and refunded to the policyholder. Accordingly, commission amounts calculated and paid shall also be refunded. | Change Request | Pending | Medium | High | Reference to the call held on 05-05-2020, it was agreed that no claim bonus concept consideration is applicable for all types of fronting policies, not only Credendo.
12 | 2020-04-12 | Agents Portal | New endorsement type is required providing the ability to amend broker commission during the policy period. | Change Request | Pending | High | High