## Category Clarification
Category | Description
Change Request | New Change Requested on the approved scope and needs development
Missing Requirement | Requirement that was mentioned in the approved scope but wasn’t delivered
Feedback needed from ICIEC | Clarifications or information need to be provided by ICIEC, however upon the feedback, the category might be changed or dropped.
Feedback needed from ESKADENIA | Verification or clarification needed from ESKADENIA
Enhancement | It’s a change requested but can be done and needs minimum development effort by the team
Setup Configuration | If minor update required on the defined setup
Credit Insurance Gap Verification Sessions Results
Category | Updated Number of Points | Old Number of Points
Change Request ¦ Excluding Cancelled & Closed CRs | 23 | 55
Missing Requirement | 0 | 0
Feedback needed from ICIEC ¦ Excluding Closed Points | 2 | 15
Feedback needed from ESKADENIA ¦ Excluding Closed Points | 0 | 12
Enhancement | 104 | 72
Setup Configuration ¦ Excluding Closed Points | 5 | 5
Total | 134 | 159

## Credit Gap Verification Log
# | Session Date | Module | Item | Category | Status | Priority from ESKADENIA perspective | Priority from ICIEC perspective | Remarks - ESKADENIA | Remarks - ICIEC
1 | 2020-03-01 | Setup | Credit Limit Applications and Approvals shall have different segment codes (reference numbers). | Enhancement | Pending | High | High
2 | 2020-03-01 | Setup | NBI, Application, Preliminary Application & Main Application; serials shall reset per country. | Enhancement | Pending | High | High
3 | 2020-03-01 | Setup | Policy; serials shall reset per country and policy type (product). | Enhancement | Pending | High | High
4 | 2020-03-01 | Setup | Countries; as per ICIEC IT team, more informative fields have to be applied that will be utilized for reporting and statistical purposes. | Change Request | Pending | Low | High | ICIEC has shared on 12.05.2020 the country details that shall be included as informative fields. | Already in IMS and raised during Business Requirements gathering phase
5 | 2020-03-01 | Setup | Closing Periods: possibility to add “From Date” in order to determine the interval. | Enhancement | Pending | Low | High
6 | 2020-03-01 | Data Migration | Commercial production migration Excel templates to be shared with ICIEC IT team by ESKADENIA. | Feedback needed from ESKADENIA | Closed | High
7 | 2020-03-01 | Setup | Segmentation structures shall be extracted by ESKADENIA to Excel files for verification by ICIEC IT team. | Feedback needed from ICIEC | Pending | High | High | The segmentation structure was shared with ICIEC on 16.06.
8 | 2020-03-01 | Setup | All setup data shall be extracted by ESKADENIA to Excel files to facilitate the verification by ICIEC. | Setup Configuration | Closed | High
9 | 2020-03-01 | Setup | Notifications and approvals will be shared with ICIEC in order to determine the subject, content (email body) and list of recipients. | Enhancement | Pending | High | High | As agreed, we will proceed with dummy content and subject until UAT. During End Users Training and Users Acceptance Testing ICIEC will tune them as Business Users will be seeing these notifications in action. | Agree
10 | 2020-03-01 | Data Migration | ICIEC IT team will check the possibility to create and access the views with production, claims and reinsurance data at the current database otherwise the data will be filled at the agreed upon ESKADENIA Excel templates. | Feedback needed from ICIEC | Closed | High |  | As discussed, data will be provided and filled at the agreed upon ESKADENIA Excel templates.
11 | 2020-03-03 | Business Entities | “Holding Company” label amendment to “Parent Company”. | Enhancement | Pending | Low | High
12 | 2020-03-03 | Commercial Production | “Policy Classification” option for CSTP product is “Whole-turnover Policy”. | Enhancement | Pending | Medium | High
13 | 2020-03-03 | Commercial Production | “Submission Date” label amendment to “Registration Date”. | Enhancement | Pending | Low | High
14 | 2020-03-03 | Commercial Production | “Application Date” label amendment to “NBI Validity Date” bearing in mind that once NBI is approved, decision date shall be reflected. | Enhancement | Pending | Low | High
15 | 2020-03-03 | Commercial Production | “Eligibility Criteria”; possibility to automatically answer certain eligibility questionnaire’s questions without having to manually insert them e.g. “Is the applicant from a member country?” as the applicant’s country is already captured along with the business entity details. | Enhancement | Pending | Medium | High
16 | 2020-03-03 | Commercial Production | DCIP product, if premium type is “Standard” then option to specify the confirmation rate’s percentage shall be available (by default set to 70%). | Enhancement | Pending | High | High
17 | 2020-03-03 | Commercial Production | Credit Limit Applications; as during the offer preparation, request to assess buyers in order to identify indicative limits is very important to BDD therefore option to perform credit risk assessment by applying/filling credit limit applications for the respective major buyers for NBI purposes only without any further or additional impact shall be available. Other than that, credit limit applications will be utilized to issue approvals, as per the implemented behavior. | Enhancement | Pending | High | High
18 | 2020-03-03 | Commercial Production | NBI Segment Code (Reference No.): as currently ICIEC applies same segment code to both NBIs and Applications, separate segment structure shall be defined at setup for NBIs in order to properly identify and distinguish each document type. | Setup Configuration | Pending | Low | High
19 | 2020-03-03 | Commercial Production | “New Version” and “Convert to Application”: current implemented behavior and feature shall be preserved yet replicated to provide the possibility of creating a new version or accept and convert NBI to application with same or different terms. | Enhancement | Closed | Medium
20 | 2020-03-03 | Commercial Production | Automatic signature or e-signature possibility implementation to the printouts (reports). | Change Request | Pending | Medium | Medium
21 | 2020-03-04 | Commercial Production | Possibility to select multiple cases and then bulkily apply transactions to them with proper comments (e.g. approve). | Change Request | Cancelled | Low | Medium | For the sake of accuracy and verification, it is recommended to apply transactions and decisions on single selections.
22 | 2020-03-04 | Commercial Production | For STP, DCIP and investment (sovereign) products, option to provide customer the facility to specify no. of days in year is required (mainly when banks are involved). | Enhancement | Pending | Medium | High |  | Already in IMS and raised during Business Requirements gathering phase
23 | 2020-03-04 | Commercial Production | “Max. Credit Period Unit”, field shall be disabled and set to “Days” by default. | Enhancement | Pending | Low | High |  | The default should be days or blank "mandatory" to be checked
24 | 2020-03-04 | Commercial Production | “Declaration Frequency” shall be set to optional and “Single” option shall be renamed to “Open”. | Enhancement | Pending | Low | Low | According to the call held on 04-05-2020, it was agreed to keep it available under the NBI, Application & Policy as optional.
25 | 2020-03-04 | Commercial Production | “Min. Premium Balance” field’s label shall be changed to “Min. Premium”. | Enhancement | Pending | Low | High
26 | 2020-03-04 | Commercial Production | Scroll up option possibility addition. | Enhancement | Cancelled | Low | Medium | Scrollbar facility is already available to perform scroll down and scroll up within the page. | Already in IMS and raised during Business Requirements gathering phase (Scroll Bar is already there)
27 | 2020-03-04 | Commercial Production | Addition of “Reason of Submission” at NBI, Application and Policy level. | Enhancement | Pending | Medium | High
28 | 2020-03-04 | Commercial Production | Scheduled job definition according to which expired policies’ status will change to “Expired” automatically. | Enhancement | Pending | Medium | Medium
29 | 2020-03-04 | Commercial Production | For BMP product, feedback is required from ICIEC regarding “Declaration of Effected Transactions” related to application’s insurance terms. | Enhancement | Closed | Medium | Medium | According to the call held on 04-05-2020, it was agreed to keep it as optional.
30 | 2020-03-04 | Commercial Production | Upon completion of NBIs, Applications and Policies’ details, option is requested providing the possibility to display all filled details in preview mode (disabled); however, if user decides to change any of the details, then “Edit” option shall redirect user to the respective section. | Enhancement | Pending | Medium | High |  | In IMS already. Enhancement of data integrity and correctness (should be available) (Radwan to re-think about it)
31 | 2020-03-05 | Commercial Production | “Loss Payee Assignment” endorsement - Possibility to specify and assign a loss payee for a whole policy, specific buyer/s or certain declaration/s. | Enhancement | Pending | High | High |  | Already in IMS and raised during Business Requirements gathering phase
32 | 2020-03-05 | Commercial Production | “Loss Payee Assignment” endorsement - When a loss payee (bank) is linked to a buyer and the approved upon credit limit is changed, then automatic notification shall be directed to the bank. | Setup Configuration | Pending | Medium |  | New notification process shall be defined for this purpose.
33 | 2020-03-05 | Commercial Production | “Loss Payee Assignment” endorsement - For STP product only, it is possible to specify compensation share percent or amount. | Enhancement | Pending | Low | High
34 | 2020-03-05 | Commercial Production | “Loss Payee Assignment” endorsement - No loss payee reinstatement option shall be available. | Enhancement | Pending | Low | Medium
35 | 2020-03-05 | Commercial Production | “Loss Payee Assignment” endorsement - “Loss Payee relation with Policyholder” field shall be removed. | Enhancement | Pending | Low | Low
36 | 2020-03-05 | Commercial Production | “Covers (Risk Types) Modification” endorsement - Possibility to specify and adjust the rate (apply loading/discount) at newly added covers (risk types) controlled by the DoA. | Change Request | Pending | High | High
37 | 2020-03-05 | Commercial Production | “Policyholder Personal Details Modification” endorsement - Possibility to minimize the details that can be amended through endorsement option. | Enhancement | Pending | Low | Medium
38 | 2020-03-05 | Commercial Production | “Cancellation” endorsement - premium refund is possible whenever applicable i.e. if minimum of premium was applied at policy level. | Enhancement | Pending | High | High
39 | 2020-03-05 | Commercial Production | Document wordings shall be available at endorsement level. | Enhancement | Pending | Medium | Medium |  | According to the call held on 04-05-2020, each endorsement has standard clauses and any amendment shall follow the DoA. It is preferable to keep them as one endorsement i.e. implementation of wordings (clauses, conditions and terms) consideration with the endorsement/change itself.
40 | 2020-03-05 | Commercial Production | Automatic notification shall be directed to the client before 3 months of the policy expiry. When 2 months are remaining for the policy expiry, a new case (i.e. automatic creation of a renewal policy) shall be performed to proceed with communication and negotiation with the client. Upon approval of renewal and on the renewed policy’s effective date, linked and related approvals shall also be renewed bearing in mind that policy’s terms and rates shall be applied and reflected accordingly; however, exceptional cases should keep and preserve the old terms and rates applied. | Enhancement | Pending | Medium | High
41 | 2020-03-05 | Commercial Production | “Subsidiaries Addition” endorsement: feedback is required from ICIEC to identify whether list of subsidiaries shall be considered as business entities and added with full or basic details. | Feedback needed from ICIEC | Closed | Low |  | According to the call held on 04-05-2020, for subsidiaries, if no separate statement of account and no access to the portal is required, then we can define them with minimal information through "Subsidiaries Addition" endorsement. Otherwise, they have to go through the whole process (i.e. consider as standalone entity), with the possibility to link between master and sub-policy.
42 | 2020-03-05 | Commercial Production | Endorsements printouts: feedback is required from ICIEC if any specific printouts (reports) shall be available for endorsements. | Change Request | Pending | Medium | High |  | Yes it is required by ICIEC
43 | 2020-03-08 | Commercial Production | Addition of comments at credit limit applications, history tab. | Enhancement | Pending | Low | Medium |  | Already in IMS and raised during Business Requirements gathering phase
44 | 2020-03-08 | Commercial Production | “Terms of Payment” shall be defaulted to “Open Account” option. | Enhancement | Pending | Low | High |  | to be defaulted to "blank" and Mandatory
45 | 2020-03-08 | Commercial Production | For single transaction policy types (e.g. STP), payment terms details such as “Selection List” shall be available at policy level. | Enhancement | Pending | Medium | High | According to the call held on 04-05-2020, this item is confirmed.
46 | 2020-03-08 | Commercial Production | “Subsidiary” label shall be changed to “Insured”. | Enhancement | Pending | Low | High
47 | 2020-03-08 | Commercial Production | Split the information and entry details of CLA sections to avoid confusion (i.e. design of relevant details shall be put within a panel or field-set). | Enhancement | Pending | Low | High
48 | 2020-03-08 | Commercial Production | “Cover Scope” label shall be changed to “Scope of Cover” providing the facility of multi-selection. | Change Request | Cancelled | Low | High | Label will be changed however addition of covers will take place one by one to assure data integrity and accuracy.
49 | 2020-03-08 | Commercial Production | “Goods/Services” section, only one sector and sub-sector is required while sector1 and sector2 options shall be removed. | Enhancement | Pending | Low | High
50 | 2020-03-08 | Commercial Production | “Goods/Services” section, under sector options, “Others” option shall also be added in addition to the defined list of items whereby user/policyholder will have the facility to define the details in a free text. | Change Request | Cancelled | Medium | Medium |  | This request is already in IMS NS also required in the customer portal. If sector is entered no "other" options should be available. The sector list is configurable any new sector can be added, it is not recommended to put "Other" to enhance the structure of data in the system and enhance reporting.
51 | 2020-03-08 | Commercial Production | “Risk Type”: 1. If policyholder and buyer are located in the same country, then risk type field shall be automatically set to domestic. 2. If buyer is located in free zone, then risk type field shall be automatically set to export. | Enhancement | Pending | Low | High
52 | 2020-03-08 | Commercial Production | “Trade and Payment Experience” between the policyholder and buyer shall be implemented at CLA level. | Enhancement | Pending | Medium | High |  | In IMS
53 | 2020-03-08 | Commercial Production | Guarantor represents the ultimate risk and shall be defaulted in case of a single guarantor; however, if more than one is available, then ultimate risk shall be manually specified bearing in mind that the risk is linked with the guarantor rather than the buyer. | Enhancement | Pending | Medium | High
54 | 2020-03-08 | Commercial Production | CLA pricing, possibility to merge loading and discount fields to a single entry whereby rate adjustment will be controlled by plus/minus values. Furthermore, if discount is applied, justification/notes shall be mandatory. | Enhancement | Pending | Low | High |  | Already in IMS and raised during Business Requirements gathering phase (keep both separated and make the justification text mandatory if value is entered)
55 | 2020-03-08 | Commercial Production | Additional supporting details that facilitate the assessment process are required such as: 1. Percentage of Acceptance 2. Ceded Amount 3. Net Amount 4. Utilization 5. Exposure 6. Outstanding NPLs 7. Claims | Feedback needed from ESKADENIA | Closed | High | High | Further to the session held about ESKA Analytics & the call to discuss the dynamic & flexible implementation of Financial Statements (e.g. Balance Sheet, Income Statement etc.) import, additional ratios & measurements can be generated using ESKA Analytics. | Already in IMS and raised during Business Requirements gathering phase - A Session on Eska Analytics is required to be held so that a precise decision will be taken on how to proceed with this item.
56 | 2020-03-08 | Commercial Production | “Calculated” and “Standard Rate” labels shall be reversed. | Enhancement | Pending | Low | High
57 | 2020-03-08 | Commercial Production | “Preferred Rate” shall be also captured at CLA level. | Enhancement | Pending | Medium | High
58 | 2020-03-08 | Commercial Production | “Indicative Rate” and “ICIEC Share” fields are not applicable for BMP policy type, only for DCIP. | Enhancement | Pending | Low | High
59 | 2020-03-08 | Commercial Production | Applied and approved limit shall not exceed available buyer capacity (link OCL with ICLs). | Enhancement | Pending | High | High
60 | 2020-03-08 | Commercial Production | Legal: 1. Policy wordings shall not be amended at policy level as these are standard and approved upon terms and conditions but should follow the endorsements process in order to properly trace and identify changes. 2. No possibility to re-process (i.e. reverse) endorsements shall be possible for any reason while possible correction or amendment shall take place through addition of a new endorsement. | Enhancement | Pending | High | High
61 | 2020-03-08 | Commercial Production | Legal: 1. At Credit Limit Applications, option is required to exclude certain risk (cover) types. | Change Request | Pending | Medium | High
62 | 2020-03-08 | Commercial Production | Feedback and confirmation are required from ICIEC whether subsidiaries and respective credit limit applications will be addressed under a single policy or treated as different policies. | Feedback needed from ICIEC | Closed | Medium | Medium | Same as #41. Option is available and implemented in the system.
63 | 2020-03-08 | Commercial Production | Feedback is required from ICIEC whether we need to specify percentages per guarantor or not. | Enhancement | Pending | Medium | Medium |  | Yes, if there is more than one guarantor, then at the level of each guarantor (Br. Radwan to check the current setup and assess).
64 | 2020-03-08 | Commercial Production | ESKADENIA shall review CLA forms to verify that all enclosed details are reflected at the system (e.g. DCIP policy type). | Enhancement | Pending | High | High | ESKADENIA will review the provided CLA forms and will reflect them to the system.
65 | 2020-03-08 | Commercial Production | Feedback is required from ICIEC to specify the additional supporting details that facilitate the assessment process. | Feedback needed from ICIEC | Closed | High | High | Further to the session held about ESKA Analytics & the call to discuss the dynamic & flexible implementation of Financial Statements (e.g. Balance Sheet, Income Statement etc.) import, additional ratios & measurements can be generated using ESKA Analytics.
66 | 2020-03-08 | Commercial Production | Approved “Scope of Cover” options list has been provided by ICIEC. ESKADENIA has to assure that the same items are reflected in the system. | Setup Configuration | Pending | Medium | High
67 | 2020-03-09 | Sovereign Production | At “Enquiry” page, addition of further options to search and filter by (e.g. investor country, host country and industry). | Enhancement | Pending | Medium | High |  | Already in IMS
68 | 2020-03-09 | Sovereign Production | Addition of “Sector” option specification at both online Customer Portal and Credit Insurance. | Enhancement | Pending | Medium | High |  | Sector is almost required everywhere in the data entry process and reporting.
69 | 2020-03-09 | Sovereign Production | Rename “Application” at menu to “Main Application”. | Enhancement | Pending | Low | Medium
70 | 2020-03-09 | Sovereign Production | Rename “Enquiry Details” to “Project Details”. | Enhancement | Pending | Low | Medium
71 | 2020-03-09 | Sovereign Production | Rename “Project Cost” to “Total Investment Amount”. | Enhancement | Pending | Low | Medium
72 | 2020-03-09 | Sovereign Production | “Investment Type” list shall contain only the below options: 1. Financing 2. Equity 3. Loan Guarantee 4. Others with free text specification | Change Request | Cancelled | Low | Medium |  | Already in IMS and raised during Business Requirements gathering phase (The list of investment type is configurable and ICIEC can add more investment types when needed), others is not recommended for data structure and classifications.
73 | 2020-03-09 | Sovereign Production | “Project Description” field shall be multi-line. | Enhancement | Pending | Low | Medium | No development is required, only field style change.
74 | 2020-03-09 | Sovereign Production | At NBI report: 1. Point #8 shall be removed. 2. Apply the possibility to display rates both per annum and as flat rate. 3. Terms and Conditions shall reflect the added conditions at enquiry level. | Enhancement | Pending | Medium | High
75 | 2020-03-09 | Sovereign Production | NHSO and FIPF products, possibility to add one or multiple banks whereby one of these banks will be the agent (leader) and the others participating alone with the respective portion (amount) of each bank. This option shall be reflected both at the online customer portal and Credit Insurance system. | Change Request | Pending | High | High |  | Already raised during the Business Requirements phase (ESKA with review the recording for this Item)
76 | 2020-03-09 | Sovereign Production | Further to the above point, new endorsement type “Policy ownership transfer” is required for either full or partial ownership transfer. | Change Request | Pending | High | High
77 | 2020-03-09 | Sovereign Production | Feedback is required from ICIEC whether “Investor’s Contribution List” shall be removed. | Feedback needed from ICIEC | Closed | Low | Medium | According to the call held on 06-05-2020, it was agreed to rename the title to "Investor's contribution for which insurance is required" as written in the main application and preserve the same content (list of options).
78 | 2020-03-10 | Sovereign Production | “Percentage of Cover %” field is not required at cover level and shall be removed. | Enhancement | Cancelled | Low | Medium | According to the call held on 06-05-2020, “Percentage of Cover %” field shall not be removed and will be kept as it is required.
79 | 2020-03-10 | Sovereign Production | Text fields shall be enlarged and changed to multi-line. | Enhancement | Pending | Low | Medium
80 | 2020-03-10 | Sovereign Production | Rename “Proportion of Investment Allocation” to “Investment Amount Allocation” whereby percent shall be replaced with amount specification and addition of the following options: 1. Financing 2. Guarantee 3. Others and to mention. | Enhancement | Pending | Medium | High | According to the call held on 06-05-2020, “Equity" option shall be added to the list of options.
81 | 2020-03-10 | Sovereign Production | Rename “CRAD Rating” to “Country Risk Rating”. | Enhancement | Pending | Low | High
82 | 2020-03-10 | Sovereign Production | “Rating” column shall be removed from “Risk Rating” section. | Enhancement | Pending | Low | High
83 | 2020-03-10 | Sovereign Production | Align “Risk Mitigant” to be placed before “Risk Rating”. | Enhancement | Pending | Low | Medium
84 | 2020-03-10 | Sovereign Production | New stage addition “Due Diligence”. | Enhancement | Pending | High | High
85 | 2020-03-10 | Sovereign Production | “Shares Details” shall appear only for FIPE product (equity) at preliminary application level. | Enhancement | Pending | Medium | Medium
86 | 2020-03-10 | Sovereign Production | Rename “Economic Impact” to “Development Impact”. | Enhancement | Pending | Low | Medium
87 | 2020-03-10 | Sovereign Production | “Investment Experience” shall be re-allocated at the applicant profile level. | Enhancement | Pending | Medium | Medium |  | Already in IMS at the main application level
88 | 2020-03-10 | Sovereign Production | Rename “Rate” to “On Risk Rate”. | Enhancement | Pending | Low | High
89 | 2020-03-10 | Sovereign Production | Possibility to apply loading or discount to the calculated rates (pricing). | Enhancement | Pending | Medium | High | Discount is available yet loading requires development. | Already in IMS and raised during Business Requirements gathering phase
90 | 2020-03-10 | Sovereign Production | Change “Stage” to “Status” at Policies list. | Enhancement | Pending | Low | High
91 | 2020-03-10 | Sovereign Production | Rename “Headquarter” branch name to “Headquarters”. | Enhancement | Pending | Low | High
92 | 2020-03-10 | Sovereign Production | Rename “Term Duration” to “Covered Period”. | Enhancement | Pending | Low | High
93 | 2020-03-10 | Sovereign Production | Reinsurance input, feedback and integration shall be applied at enquiry level. | Enhancement | Pending | High | High
94 | 2020-03-10 | Sovereign Production | Rename “Inward” to “Inward Reinsurance”. | Enhancement | Pending | Low | High
95 | 2020-03-10 | Sovereign Production | ICIEC raised concern about IIPG automatic meeting handling through the system. | Feedback needed from ESKADENIA | Closed | Low |  | All meetings will be handled outside the systems, and the Minutes of Meeting document will be uploaded to the system and archived in the DMS as per the approved scope under the Credit BRD.
96 | 2020-03-10 | Sovereign Production | Eligibility questionnaires applied for sovereign products have to be verified with Legal. | Feedback needed from ICIEC | Closed | High | High | According to the call held on 06-05-2020, eligibility for sovereign shall be implemented as an approval process whereby the case will be directed to legal department for verification and decision.
97 | 2020-03-10 | Sovereign Production | For “Preliminary Application Form”, section 9.0 in the report, feedback and clarification are required from ICIEC. | Feedback needed from ICIEC | Closed | Medium |  | According to the call held on 04-05-2020, this item shall be kept as in the "Preliminary Application Form" bearing in mind that more options can be added later.
98 | 2020-03-10 | Sovereign Production | Possibility to amend submission report printout whereby changes shall be stored and made available for other users to preview and further amend (changes might include but not limited to text, graphs, images, videos etc.). | Change Request | Pending | Low | High | The possibility to add any new sections to the submission report (a header of section to be filled and a text area of the section to be filled) so that ICIEC Users can add any new section(s) other than fixed sections (such as COVD-19 impact) to the submission report. The submission report screen will have fixed sections as per the sample reports we sent to you and some dynamically added sections than can be introduced and filled. | ICIEC will check for further information.
99 | 2020-03-10 | Sovereign Production | At submission level, provision of a summary report with details and graphs to facilitate the UW assessment process. | Enhancement | Pending | Medium | High |  | Similar to item 98 - Already requested during Business Requirements gathering.
100 | 2020-03-10 | Sovereign Production | ESKADENIA has to review main policy submission form to assure that all mentioned details are reflected in the “Project Summary” section. | Enhancement | Pending | High | High
101 | 2020-03-10 | Sovereign Production | Possibility to import disbursement and repayment schedules through pre-defined excel template along with graphical presentation of exposure curve. | Change Request | Pending | Medium | High |  | Requested during the Business Requirements gathering phase .
102 | 2020-03-11 | Production Financial Integration | Minimum of premium invoice shall impact customer at both the voucher’s sides and affect different account. | Enhancement | Pending | High | High
103 | 2020-03-11 | Production Financial Integration | Upon each monthly invoicing of declarations, reconciliation with minimum of premium, if applicable, shall take place bearing in mind that at the end of the period, if reconciled amount exceeds the minimum of premium, adjustment to the broker’s commission shall also occur. | Change Request | Closed | High | High | Refer to point #154, as it will be merged in one point. | Refer to Item # 154
104 | 2020-03-11 | Production Financial Integration | Rename “Un-post” functionality to “Reverse”. | Enhancement | Closed | Low | High | Amended and reflected.
105 | 2020-03-11 | Production Financial Integration | Minimum of premium handling shall be specified at policy level to identify whether any surplus paid in advance shall be treated as a customer refund or directed to charity (Waqf). | Change Request | Closed | Medium | Medium | Refer to point #154, as it will be merged in one point. | Refer to Item # 154
106 | 2020-03-11 | Production Financial Integration | ESKADENIA shall share all handled and implemented Financial transaction types to be reviewed by ICIEC for the chart of accounts consideration purpose. | Feedback needed from ESKADENIA | Closed | Medium | High | Please refer to sheet "Transaction Types" sheet.
107 | 2020-03-11 | Production Financial Integration | Financial integration for Credit Information sources shall be amended to post the total amount at the end of the month per source rather than on transaction basis (one by one). | Enhancement | Pending | Medium | High
108 | 2020-03-11 | Production Financial Integration | Further discussion is required about unearned premium calculations and posting to the Financial entity (ESKADENIA and ICIEC). | Change Request | Pending | High | High | Unearned premium calculations and posting to the financial entity. Based on the template provided by ICIEC. | to be discussed with ICIEC (Br. Ali)
109 | 2020-03-11 | Production Financial Integration | Possibility to generate customer statement of account from technical side (Credit) in order to avoid presenting posted and reversed transactions as the customer shall be considered only about confirmed transactions. | Change Request | Cancelled | Low |  | It was agreed to drop this item and maintain the implemented current system behavior.
110 | 2020-03-11 | Production Financial Integration | Feedback is required from ICIEC whether to provide option of due premiums extension with premium or without. | Enhancement | Pending | High | High | According to the call held on 04-05-2020, it was agreed to split this point into two items, one for buyer's payments extension and one for policyholders' premium invoices' extension (refer to new gap point #163). The option to provide extension of buyers' payments extension shall be available in the system.
111 | 2020-03-22 | Claims | At both NPLs and Claims pages, at policyholder section, addition of respective sector and sub-sector informative details. | Enhancement | Pending | Low | High |  | Sector is required almost everywhere
112 | 2020-03-22 | Claims | “Branch” field shall reflect by default the relevant policy’s branch (office). | Enhancement | Pending | Low | High
113 | 2020-03-22 | Claims | “Invoices” tab, addition and display of the respective month for each declaration. | Enhancement | Pending | Medium | High
114 | 2020-03-22 | Claims | “Loss Date” and “Credit Period” fields are no longer relevant and can be removed as multiple approvals and invoices can be linked at NPL and Claim pages level. | Enhancement | Pending | Low | High
115 | 2020-03-22 | Claims | “Exchange Rate” field shall be removed and applied at “Invoices” tab instead. | Enhancement | Pending | Medium | Medium
116 | 2020-03-22 | Claims | “Invoices” tab, addition of “Shipment No.” and “Loss Amount” specification facility. | Enhancement | Pending | High | High
117 | 2020-03-22 | Claims | “Pre-Shipment Details” section shall be visible only if the pre-shipment covered risk is available at respective policy level. | Enhancement | Pending | Medium | High
118 | 2020-03-22 | Claims | Claim amount shall be limited to the approval amount rather than the declaration/shipment amount as the policyholder might ship more than the approved. | Enhancement | Pending | High | High
119 | 2020-03-22 | Claims | For STP (Single Transaction Policy) and Investment policy types, each repayment shall be displayed and presented individually in case of non-payment. | Enhancement | Pending | High | High
120 | 2020-03-22 | Claims | Whenever an NPL is registered, then all buyer’s active ICLs and OCLs shall be cancelled. However, if the NPL is cancelled, then the ICLs and OCLs shall be restored. | Enhancement | Pending | High | High | This was also requested with the 2nd batch of enhancements. | Whenever an NPL is registered, then all buyer’s active ICLs and OCLs shall be cancelled. (if the NPL is cancelled, then the ICLs and OCLs shall be restored) is not required anymore
121 | 2020-03-22 | Claims | Possibility to capture details of partial payments (date, amount and notes). | Enhancement | Pending | High | High |  | Already in IMS and raised during Business Requirements gathering phase
122 | 2020-03-22 | Claims | Loss payee details shall be reflected automatically without any manual insertion. | Change Request | Pending | Low | High
123 | 2020-03-22 | Claims | At the event of claim approval, subrogation letter has to be provided by the policyholder; option is required to perform this online. | Enhancement | Pending | Low | High |  | To be done through Notification process.
124 | 2020-03-22 | Claims | Possibility to specify fees and expenses at expected recovery identification. | Change Request | Pending | Medium | High
125 | 2020-03-22 | Claims | Consideration of “Write Offs” as standalone functionality whereby details are similar to recovery process. | Enhancement | Pending | High | High | Needs development but its mentioned in the operational manual so its considered an enhancement.
126 | 2020-03-23 | Claims Financial Integration | Posting of NPL while also taking into consideration the reversal transaction that has to take place when NPL is materialized into claim. | Enhancement | Pending | Medium | High | Posting NPL is already implemented, while the reversal transaction when NPL is materialized into claim needs development.
127 | 2020-03-23 | Claims Financial Integration | Further discussion is required between ESKADENIA and ICIEC as with respect to the expected recovery financial integration handling whether it shall be treated as revenue or not. | Feedback needed from ICIEC | Closed | Low |  | It was agreed to drop this item and maintain the implemented current system behavior.
128 | 2020-03-23 | Claims Financial Integration | Upon amendment of the expected recovery, reversal of previously generated financial transaction shall occur and generation of new ones shall take place instead. | Change Request | Closed | Low |  | It was agreed to drop this item and maintain the implemented current system behavior.
129 | 2020-03-24 | Reinsurance | Provision of copy treaty option. | Enhancement | Pending | Low | Low
130 | 2020-03-24 | Reinsurance | Country limit will be captured for informative purposes only. | Change Request | Pending | Low | Low |  | Needed
131 | 2020-03-24 | Reinsurance | Option provision to retrocede ICIEC retention to other reinsurance companies (mainly for investment policy types). | Enhancement | Closed | Medium |  | This option is already available as users may manually adjust the reinsurance distribution and retrocede to other reinsurance companies.
132 | 2020-03-24 | Reinsurance | Hybrid commission consideration (applicable for short term treaties) whereby commission might be a certain percent of number of years (e.g. 5 years) while it will be calculated according to the loss ratio sliding scales afterwards. | Change Request | Pending | Medium | Medium |  | Commission details were discussed during Requirements Gathering / Gap Requirements May and July 2019) (Eskadenia to check further)
133 | 2020-03-24 | Reinsurance | Specification of treaty maximum limits whereby option shall be provided to specify limits per entity (buyer/bank) for both ICIEC (discretionary limit) and reinsurer. | Change Request | Pending | Medium | High |  | Already in IMS. Detail discussion of Requirements Gathering / Gap Requirements during May and July 2019 (Eskadenia to Check further)
134 | 2020-03-24 | Reinsurance | Possibility to import included and excluded countries through excel. | Change Request | Cancelled | Low | Low |  | Not a change request, part of requirements (treaty copying / cloning) - Treaties cloning and copying is already in the system (to drop the import option).
135 | 2020-03-24 | Reinsurance | Feedback is required from ICIEC regarding old treaties details (conditions and exclusions). | Feedback needed from ICIEC | Pending | Medium | Medium | ICIEC has provided only 2019 treaties and one 2020 treaty. | all treaties (for the last 4 years) conditions will be provided to be included in the treaty definition module (setup)
136 | 2020-03-24 | Reinsurance | Feedback is required from ICIEC about linking treaty programs with Credit Information sources. | Enhancement | Pending | Low | Medium | Feedback needed from ICIEC | Already in IMS. Underwriting support credit opinion should appear for Reinsurance Team to see it.
137 | 2020-03-24 | Reinsurance | Additional session shall be held by ESKADENIA with ICIEC to discuss and verify inward reinsurance policies and process. | Feedback needed from ESKADENIA | Closed | High |  | Session held on 15.04
138 | 2020-03-25 | Reinsurance | Approval process shall be implemented to assure that no facultative voucher is generated unless respective and related premiums have been collected. | Setup Configuration | Pending | Medium | High
139 | 2020-03-25 | Reinsurance | Turnover (business insured) to be considered and included in reinsurance reporting of treaty statement. | Enhancement | Pending | Medium | High
140 | 2020-03-25 | Reinsurance | Generic discussion is required with ICIEC and ESKADENIA regarding the possibility to impact existing financial transactions and reflect changes whenever accounts integration setup is amended at Credit side. | Feedback needed from ICIEC | Closed | Low |  | It was agreed that this will be handled through scripts rather than system option.
141 | 2020-03-25 | Reinsurance | Generic discussion is required with ICIEC and ESKADENIA regarding verification of transactions prior to actual posting to the Financial entity. | Feedback needed from ICIEC | Closed | Low |  | It was agreed to drop this item and maintain the implemented current system behavior.
142 | 2020-03-25 | Reinsurance | Option provision to specify whether fees and expenses shall be included or excluded from reinsured premium for both treaty and facultative distribution. | Change Request | Pending | Medium | Medium
143 | 2020-03-25 | Reinsurance | For ST (Short Term) and MT (Medium Term) policy types, reinsurance shall take place on approval level while for LT (Long Term) and Investment policy types it shall occur on policy level. | Change Request | Pending | Medium | High | MT and LT automatic approval will be generated in the backend. However, Reinsurance will take place at policy level. ST will remain as is. | Already in IMS. CORRECTION : For ST (Short Term) policy types, reinsurance shall take place on approval level while for MT (Medium Term) and LT (Long Term) and Investment policy types it shall occur on policy level.
144 | 2020-03-25 | Reinsurance | Additional session shall be held by ESKADENIA with ICIEC to discuss and verify non-proportional treaties (XoL). | Feedback needed from ESKADENIA | Closed | Medium
145 | 2020-03-29 | Declarations | Addition of dates range fields as search criteria. | Enhancement | Pending | Medium | Medium |  | Dates are essential in any search criteria
146 | 2020-03-29 | Declarations | “Received Date” field shall be amended to optional. | Enhancement | Pending | Medium | Medium
147 | 2020-03-29 | Declarations | Addition of “Shipment Date” field along with “Declaration Date”. | Enhancement | Pending | Medium | High
148 | 2020-03-29 | Declarations | Implementation of control whereby declarations after allowed period (15 days of next month) shall remain pending until reviewed and verified by ICIEC whereby decision will be eventually applied either with acceptance or rejection. | Change Request | Cancelled | Medium | High | Further to the call held with ICIEC IT, it has been agreed to control the number of allowed days through setup. Whenever, exceptions are required, ICIEC IT will change the setup accordingly. | Keep the same setup and whenever ICIEC decide to allow a declaration after 15 days, ICIEC IT will change the setup for the case and return back.
149 | 2020-03-29 | Declarations | Addition of declaration amount field in local currency that will be disabled and automatically filled upon insertion of the declaration amount and exchange rate. | Enhancement | Pending | Low | High |  | Already in IMS
150 | 2020-03-29 | Declarations | Possibility to bulk import shipments through pre-defined excel template. ESKADENIA shall provide suggestions if this option would be viable taking into consideration complications that might result and arise. Eventually, ICIEC will decide whether to implement this option or not. | Change Request | Cancelled | Medium | Medium | According to the call held on 04-05-2020, import using a pre-defined excel template will take place whereby the correct transactions will be accepted while the faulted ones will be logged providing the facility to fix them online. | Cancelled by ICIEC on 21.06.2020
151 | 2020-03-29 | Declarations | Further feedback is required from ICIEC regarding declarations above the approved limit whether this will be allowed or not and if we should charge for the excess. | Change Request | Pending | Low | High | According to the call held on 06-05-2020, declaration above the approved limit shall always be allowed. However, we need to add an option at policy level according to which we can determine whether to charge for the excess or not.
152 | 2020-03-29 | Declarations | Option has to be applied at policy level to specify whether declarations’ exchange rate will be automatically captured or manually specified. | Change Request | Pending | Medium | High
153 | 2020-03-29 | Declarations | ESKADENIA shall provide declarations’ details per policy type for ICIEC to review and confirm or feedback, if any. | Enhancement | Pending | High | High
154 | 2020-03-29 | Declarations | Reconciliation decision has to be applied with three options (1. Revolve 2. Refund 3. Waqf) according to which respective transactions will be generated. | Change Request | Pending | Medium | Medium |  | Related to item # 103 and to be merged together
155 | 2020-03-29 | Declarations | ICIEC and ESKADENIA need to discuss possibility to retrieve list of MoPs (minimum of premiums) for aging purposes. | Feedback needed from ESKADENIA | Closed | Medium |  | Retrieval of MoP for aging purposes at the Financial system is possible.
156 | 2020-04-15 | Commercial Production | Flag addition to differentiate buyers captured either by ICIEC or through fronting. | Enhancement | Pending | Medium | Medium |  | Already in IMS
157 | 2020-04-15 | Reinsurance | Inward Reinsurance - pricing is determined by insurer and shall not be calculated according to Credit setup rather will be specified per policy. | Enhancement | Pending | High | High
158 | 2020-04-15 | Reinsurance | Feedback is required from ICIEC for Coface and Credendo treaties to be reviewed by ESKADENIA and defined in the system. | Setup Configuration | Pending | Medium | Medium | Treaties have been provided by ICIEC.
159 | 2020-04-15 | Reinsurance | Some setup such as credit limit application, buyer details and etc. are not applicable for inward quota share treaty program. Does this setup mandatory for all types of transactions or user only need to complete setup relevant or applicable to their particular transaction only? | Enhancement | Pending | High | High | Reference to the call held, it has been agreed upon that for ITQP (Inward Quota Share), credit limit applications, approvals and buyers' details will be considered as optional and can be skipped in the process of issuing a policy. | How Buyers basic data will be registered ? Especially since Reinsurance will not have the information (short session between Reinsurance and ICIEC IT Team with Eskadenia held on Monday 27th April 2020)
160 | 2020-04-15 | Reinsurance | Bulk upload feature to upload the quarterly treaty declaration or statement received from insurer. Bulk upload is also required to upload the treaty max limit by country in treaty program registration. | Enhancement | Pending | High | High | New requirement was requested by ICIEC on 16.12.2019. For the second point, please refer to point # 134. | #134 is for Outward Reinsurance Treaty, while this one is for Inward Reinsurance Treaty
161 | 2020-04-15 | Reinsurance | The inward treaty program invoicing process used in the new system is different with the current process used. For the current process, we will register the declaration received from insurer and generate the invoice. In the new system, there is a treaty statement generation for inward business. Normally, treaty statement is prepared by insurer and submitted to reinsurer for their record. For the inward treaty program, I don’t see the relevance of generating the treaty statement and more clarifications also required on how to issue invoice for inward treaty program. | Change Request | Pending | High | High | Reference to the call held, it has been agreed upon that for ITQP (Inward Quota Share), no invoice shall be issued nor any premium will be calculated. Also, no distribution will take and no treaty statement will be generated; the insurer will provide the quarterly treaty statement which will be uploaded in the system and respective details will be generated (i.e. invoice, automatic dummy approvals creation which will help identify the business insured and exposure and will be valid until the next bordereau). On a side note, the quarterly treaty statement provided, usually represents distribution to top ten countries. | Linked to item # 159 also. (short session between Reinsurance and ICIEC IT Team with Eskadenia held on Monday 27th April 2020)
162 | 2020-04-15 | Reinsurance | Inward facultative reinsurance program can also be retroceded automatically to the ICIEC outward treaty (ST Treaty or MT & FII Treaty) and follow the same treaty terms and conditions as direct business such as ICIEC discretionary limit, leader limit, excluded countries etc. | Change Request | Pending | High | High | Reference to the call held, it has been agreed upon that for ITQP (Inward Quota Share), no invoice shall be issued nor any premium will be calculated. Also, no distribution will take and no treaty statement will be generated; the insurer will provide the quarterly treaty statement which will be uploaded in the system and respective details will be generated (i.e. invoice, automatic dummy approvals creation which will help identify the business insured and exposure and will be valid until the next bordereau). On a side note, the quarterly treaty statement provided, usually represents distribution to top ten countries. | Already in IMS. More discussion on this item with Eskadenia (Reinsurance, BBD and Underwriting) (This Item was raised by DAAS during the Gap Verification Session) (to be checked by Eskadenia)
163 | 2020-05-04 | Production Financial Integration | Provide option of policyholders' due premiums extension for aging purposes. | Change Request | Pending | Low | High | According to the call held on 04-05-2020, this item is newly been added.