## Category Clarification
Category | Description
Change Request | New Change Requested on the approved scope and needs development
Missing Requirement | Requirement that was mentioned in the approved scope but wasn’t delivered
Feedback needed from ICIEC | Clarifications or information need to be provided by ICIEC, however upon the feedback, the category might be changed or Dropped.
Feedback needed from ESKADENIA | Verification or clarification needed from ESKADENIA
Enhancement | It’s a change requested but can be done and needs minimum development effort by the team
Setup Configuration | If minor update required on the defined setup
Customer Portal Gap Verification Sessions Results
Category | Updated Number of Points | Old Number of Points
Change Request | 6 | 12
Missing Requirement | 0 | 0
Feedback needed from ICIEC | 0 | 0
Feedback needed from ESKADENIA | 0 | 1
Enhancement | 14 | 7
Setup Configuration ¦ Excluding Closed Points | 24 | 26
Total | 44 | 46

## Credit CP Gap Verification Log
# | Session Date | Module | Item | Category | Status | Priority from ESKADENIA perspective | Priority From ICIEC perspective | Remarks - ESKADENIA | Remarks - ICIEC
1 | 2020-03-02 | Customer Portal | Registration process; possibility and option to register as individual shall be removed as it is not viable. | Enhancement | Pending | Low | High
2 | 2020-03-02 | Commercial | “Preferred Policy Language” option shall be adjusted to consider only two options (English & Arabic). | Setup Configuration | Closed | Low |  | However this request was changed later by ICIEC on 08.04 - Check point # 43 below.
3 | 2020-03-02 | Commercial | “Policy Currency” option shall be adjusted to consider only two options (USD & EUR) rather than displaying all available currencies. | Setup Configuration | Closed | Medium
4 | 2020-03-02 | Commercial | Implementation of an additional step prior to submission whereby all previously filled information will be only displayed for review by prospect to confirm that information is in place. | Change Request | Cancelled | Low | Medium | Throughout the customer journey, user will fill the available information having the facility to move forward or backwards to review, amend and confirm the data without the need to display everything again in a single page (bearing in mind that the details will be a lot to display in a single page which can impact user experience). | This option has been discussed during the gap requirements. Client will select which section needs to be corrected and the system will allow him / her to correct
5 | 2020-03-02 | Commercial | “Contact Persons”, option shall be mandatory and prospect must not be able to proceed to latter stages unless at least one contact person has been provided. | Enhancement | Pending | Low | High
6 | 2020-03-02 | Commercial | “Declarations” option shall be split into separate global components (each row into a single component) and re-used at all products so as any amendment is applied and reflected once. | Setup Configuration | Closed | Low
7 | 2020-03-02 | Commercial | “Date of Commencing Business” can be less than “Date of Incorporation”. | Setup Configuration | Pending | Low | Low
8 | 2020-03-02 | Commercial | DCIP: Section “Losses Incurred”, change label of “Buyer” to “Bank”. | Setup Configuration | Pending | Medium | High
9 | 2020-03-02 | Commercial | DCIP: Addition of a new section at Trade Finance Business step (3rd step) to capture “Trade History” details. | Setup Configuration | Pending | High | High
10 | 2020-03-02 | Commercial | DCIP: At Declarations step (4th step), “Brochure on the Applicant and its activities (Bank Profile)” shall be optional. | Setup Configuration | Pending | Low | Medium | No development is required only change to attachments' properties. | Brochure should be attached at the DCIP Policy Application stage
11 | 2020-03-02 | Commercial | DCIP: “Sector” option shall be set to “Bank & Financing Services” by default. | Setup Configuration | Pending | Low | Medium |  | If this is at the stage of Policy definition, we want the default, if it is the credit limit application, then defaulting is not required
12 | 2020-03-02 | Commercial | BMP: “Sector” option shall be set to “Bank & Financing Services” by default. | Setup Configuration | Pending | Low | Medium |  | If this is at the stage of Policy definition, we want the default, if it is the credit limit application, then defaulting is not required
13 | 2020-03-02 | Commercial | CSTP: “Business Turnover” details shall be referred to buyers rather than banks. | Setup Configuration | Pending | Low | High | No development is required only change label.
14 | 2020-03-02 | Commercial | STP: Addition of guarantor name along with buyer details. | Enhancement | Pending | Medium | High
15 | 2020-03-02 | Commercial | STP: Shipment and repayment schedule details addition. | Setup Configuration | Pending | High | High
16 | 2020-03-04 | Commercial | Further discussion is required to review Customer Portal journey in order to cover both online NBI and Application submission in order to identify necessary details and flow. | Change Request | Cancelled | High | Low |  | Reference to the call held on 03-05-2020, it has been agreed that at the current stage, this point can be dropped and will be revisited after go live to identify the required details per product.
17 | 2020-03-09 | Sovereign | For Loan Guarantee product, provide the possibility to differentiate between policy currency and local currency (“Currency of Transaction” and “Currency of Guarantee”). | Change Request | Pending | Medium | Medium
18 | 2020-03-09 | Sovereign | Apply validation to prevent input of “Host Country” similar to “Investor Country” bearing in mind that “Host Country” shall retrieve and display only member countries. | Enhancement | Pending | Low | Low
19 | 2020-03-09 | Sovereign | Removal of “Edit” option at “Covered Risks” grid at online customer portal. | Setup Configuration | Pending | Low | Medium
20 | 2020-03-09 | Sovereign | Addition of comments/notes field. | Setup Configuration | Pending | Low | Low | Informative field.
21 | 2020-03-09 | Sovereign | “Project Description” field shall be mandatory. | Setup Configuration | Pending | Low | Medium
22 | 2020-03-09 | Sovereign | Possibility to attach and upload documents prior to the online customer portal journey finalization (e.g. project brief and other documents). | Setup Configuration | Pending | Medium | Medium
23 | 2020-03-09 | Sovereign | NHSO product, addition of bank name along with company name. Either of them shall be mandatory as prospect has to fill at least one. | Enhancement | Pending | Medium | Medium |  | Both fields are Mandatory
24 | 2020-03-09 | Sovereign | “Investment” product name shall be changed to “Investment Insurance” instead. | Setup Configuration | Pending | Low | Low
25 | 2020-03-09 | Sovereign | “Currency” field’s options shall be limited to USD and EUR. | Setup Configuration | Pending | Medium | Medium |  | to be discussed with ICIEC IT to know the concept of currencies defined in the system(s)
26 | 2020-03-09 | Sovereign | Re-align “Tenor” field to be moved on the top with addition of new field, “Tenor Unit”. | Setup Configuration | Pending | Low | Low
27 | 2020-03-09 | Sovereign | Rename “Amount of Investment” to “Total Amount of Investment”. | Setup Configuration | Pending | Low | Low
28 | 2020-03-09 | Sovereign | Rename “Project Details” to “Project Description and Details”. | Setup Configuration | Pending | Low | Low
29 | 2020-03-09 | Sovereign | Rename “Cover Name” to “Covered Risk Name”. | Setup Configuration | Pending | Low | Low
30 | 2020-03-09 | Sovereign | “Percentage of Cover %” field addition as optional. | Setup Configuration | Pending | Medium | Medium | No development is required only change to field's properties.
31 | 2020-03-09 | Sovereign | After “Project Details”, addition of a new option (checkbox) “Availability of Ministry of Finance Guarantee” for Loan Guarantee product. | Change Request | Pending | Medium | High
32 | 2020-03-09 | Sovereign | Rather than applying “Delete” option, prospect has to select which covered risks are intended. | Enhancement | Pending | Low | Medium
33 | 2020-03-09 | Sovereign | Addition of “Sector” option specification at both online Customer Portal and Credit Insurance. | Enhancement | Pending | Medium | High |  | It is required everywhere and request during Gap period and in the scope
34 | 2020-03-09 | Sovereign | A fourth investment product shall be implemented at the online customer portal (Loan Guarantee). | Setup Configuration | Pending | High | High |  | In scope (setup of new products)
35 | 2020-03-09 | Sovereign | At the online customer portal, possibility to add “Other Risks” option whereby prospect will write down the additional coverage required as a free text. | Change Request | Cancelled | Low | Medium |  | To be raised again in ICIEC. It is not recommended at all since we need to keep our data structured. List of risks is configurable and new risk/s can be added in the system through the setup.
36 | 2020-04-08 | Services | Possibility to submit new buyers along with capturing of relevant address details. | Enhancement | Pending | High | High
37 | 2020-04-08 | Services | Consider entity name and number (VAT/Commercial Registration/Fiscal Code) as unique identifier to prevent duplication of business entities. | Enhancement | Pending | High | High
38 | 2020-04-08 | Services | “Declarations”, transform entry to tabular rather single insertion whereby country shall also be considered. | Enhancement | Pending | Medium | Medium
39 | 2020-04-08 | Services | "Submit NPL”, possibility to upload attachments shall also be applied. | Setup Configuration | Pending | Medium | High
40 | 2020-04-08 | Services | NPLs and claims shall be linked together whereby a prompt shall be applied to inquire the user if NPL has already been submitted; if yes, then NPL reference shall be specified. | Enhancement | Pending | Low | Medium |  | enhancement of data integrity and controlling
41 | 2020-04-08 | Services | “Credit Limit Application”, possibility to upload attachments shall also be applied. | Enhancement | Pending | Medium | High
42 | 2020-04-08 | Services | Re-order top menu with the following order: 1. Profile 2. Policy List 3. Credit Limit Application 4. Declarations 5. Submit NPL 6. Submit Claim 7. Track Claim | Setup Configuration | Pending | Medium | Medium
43 | 2020-04-08 | Services | Addition of “French” at the available communication languages bearing in mind that this will be for informative purposes and will have no impact at the schedules and reports. | Setup Configuration | Pending | Low | Low
44 | 2020-04-08 | Services | Rename “Major Clients” to “Major Buyers”. | Setup Configuration | Pending | Low | Medium
45 | 2020-04-08 | Services | “Statement of Account” feature: 1. Option addition to filter CSOA according to the Currency, Full or Outstanding Balance. 2. Implement same layout of the financial CSOA. 3. Ability to select outstanding transactions (Debit Notes) and attach the related payment (swift or bank transfer file) with automatic email notification for allocation purposes to the Financial department copying BDD (related account manager and direct manager). | Change Request | Pending | Medium | Medium |  | raised during gap assesment sessions
46 | 2020-04-08 | Services | ESKADENIA has to review provided CLA forms and verify that enclosed details are reflected at the portals whereby credit limit applications’ details differ per policy type. | Enhancement | Pending | High | High | Changed to Enhancement, The forms will be reviewed by ESKADENIA and reflected to the system
47 | 2020-06-07 | Commercial | Possibility to keep log of shareholders changes (introduction of new endorsement). | Change Request | Pending | Medium |  | New point raised during CP demo on 07.06.
48 | 2020-06-07 | Declarations | Shipment date might be different than due date than invoice date. | Change Request | Pending | Medium |  | New point raised during CP demo on 07.06
49 | 2020-06-07 | Declarations | Provision of the ability to mention whether any overdue amount that has not been paid is available. | Enhancement | Pending | Medium |  | New point raised during CP demo on 07.06
50 | 2020-06-07 | Declarations | Provision of the ability to upload shipments through pre-defined excel template. | Change Request | Cancelled |  |  | New point raised during CP demo on 07.06 but was cancelled later. We will implement the enhancement point #38 "“Declarations”, transform entry to tabular rather single insertion whereby country shall also be considered."
51 | 2020-06-07 |  | Automatic reflection of phone prefix according to selected country (personal details) under the customer portal | Change Request | Pending | Low |  | New point raised during CP demo on 07.06