## Summary
Credit Insurance Data Migration Reconciliation & Remarks Assessment Status
Data Reconciliation Completion Progress (From ESKADENIA's Perspective) = 99.6 % Excluding the requested Changes (Remarks need Development) |  |  |  | Data Reconciliation Completion Progress (From ICIEC's Perspective) = 90.5 % Including the requested Changes (Remarks need Development)
Resolution & Validation Progress Bugs, Inquiries, Data Issues and CR at no extra cost
Resolution Progress |  |  |  |  | Validation Progress
100% |  |  |  |  | 96.64%
Data Reconciliation Remarks Classification
| Total | Resolved | Validated or Answered | Notes
Bug | 51 | 51 | 48
Data Issue | 36 | 36 | 36
Changes | 115 | - | -
Change at no extra cost | 16 | 16 | 16
Inquiries | 28 | 28 | 27 | some of the previous inquiries were re-classified
Setup | 2 | 2 | 2
Missing Sheet | 2 | 2 | 2

## Reconciliation Remarks
# | Module | System Page / TAB | Policy Type | Issue Description | Point Date | Type | Status | Is Validated | Comment
1 | CIS | Credit Information Services Source |  | Read directly from the table without conducting any validation against the "Credit Information Treaties" |  | Change at No Extra Cost | Resolved | Yes
2 | Countries | Countries Represent |  | Add "Version No" on the page at once |  | Change at No Extra Cost | Resolved | Yes
3 | Portfolio Assigment | Portfolio Assignment |  | The below fields have not retrieved the migrated data: 1. Account Manager 2. Underwriting Support 3. Underwriter 4. Policy Administration Officer |  | Change |  |  | Common
4 | Commercial | Documents (NBI, Application, Policy) |  | Disable the calculation for the "Policy Expiry Date" field, which applies only to new submissions |  | Change |  |  | Common
5 | Commercial | Documents (NBI, Application, Policy) |  | Update the field "Basic Information" to be able to extend the field size |  | Change at No Extra Cost | Resolved | Yes
6 | Commercial | Documents (NBI, Application, Policy) |  | All renewals and versions to include values for (NBI No. and Application No.) under validity section, Currently the converted submission has those values. |  | Change
7 | Commercial | Documents (NBI, Application, Policy), (Agents TAB) |  | Under the "Agent" TAB The Code doesn't appear, Ex. “CSTP-SAU-00102” Version 1, “DCIP-UAE-00011” Version 17 |  | Bug | Resolved | Yes
8 | Commercial | Documents (Application) |  | Update the “NBI Acceptance Date” to read from the last NBI submission, regardless the data that migrated |  | Change
9 | Commercial | Insurance Terms |  | Change the label “Min. Premium” to “Min. Premium Balance CF” Just for GAP policy type |  | Change at No Extra Cost | Resolved | Yes
10 | Commercial / Fees | Fees |  | Include Exchange-Rate to all net fees amounts related fields, and fields rearrangment, Screenshot attached |  | Change
11 | Commercial / Fees | Fees |  | Add the ability to print the fee reports from the system page |  | Change
12 | Commercial/Fees | Fees |  | Make it possible to increase the text size for the field ”Note Reason for Credit Note” |  | Change at No Extra Cost | Resolved | Yes
13 | Commercial | Pricing |  | Do not summarize the fields “Basic Rate” and “Final Rate” for the list of “Pricing Terms Secure Business” |  | Change
14 | Commercial | Pricing |  | Update the Field “Premium Negotiation %” to have 4 decimal points |  | Bug | Resolved | Yes
15 | Commercial | Pricing |  | Disable the “Maximum Liability” field calculation for the migrated Data |  | Change |  |  | Common
16 | Commercial | Policy Expiry, Submission Reason |  | Over whole the system for data migration the data shall be presented as is without any validation, Ex. PP-PAK-00008, (Policy Expiry Date & Submission Reason, etc.) |  | Change |  |  | Common
17 | Commercial | Insurance Terms |  | Change the label “Min. Premium” to “Min. Premium Balance CF” Just for DCR policy type |  | Change at No Extra Cost | Resolved | Yes
18 | CIS | Credit Information Services / Report |  | Update the "Source" field in the grid and data entry section to read from entity roles instead of the entity itself |  | Bug | Resolved | Yes
19 | Commercial | Documents (NBI, Application, Policy) and All Sovereign Documents |  | Apply validation to the "Validity" field to reject values of zero or less |  | Bug | Resolved | Yes
20 | Commercial | Documents (NBI, Application, Policy) and All Sovereign Documents |  | Disable the calculation for the "Expiry Date" in the "NBI Section" for migrated data, regardless of the value of the "Validity" |  | Change | Canceled |  | Duplicated with point No 4
21 | Commercial | Documents (NBI, Application, Policy) |  | Make the field “Policy Classification” visible for all policy types |  | Change
22 | Commercial | Eligibility Questions |  | The question “More than 50% of the shares are hold by nationals from member country?” Appears with the wrong answer. Ex. PP-BD -00009 |  | Change
23 | Commercial | Eligibility Questions |  | For the question “More than 50% of the shares are hold by nationals from member country?” and based on the answer of the question there is a details for Shareholder has requested. |  | Change
24 | Declarations | Declarations Details |  | Update the system pages to ensure that the “Adjustment Amount” field is visible for all policy types, Currently the field appear for Inward policies |  | Change
25 | Commercial | Pricing Page |  | The page design should be according to "Product Type", and sometimes the page design is not fetched the fields. |  | Change
26 | Commercial | Inward RI Page / Treaty Detail TAB/ Scope of cover under "Treaty Terms and Conditions" radio button |  | The Date format is incorrect for “Inception date”, Ex. Application “PP-KHZ-00008”, the Date format should be dd/Mon/yyyy |  | Bug | Resolved | Yes
27 | Commercial | Inward RI/ Treaty Detail/ Account Terms |  | Hide the Exchange Rate fields from the system page. |  | Change
28 | Commercial | NBI, Application and Policy |  | “No Of installments” does not appear on the main page of the policy (Already mentioned in CR "Additional Fields"). |  | Inquiry | Resolved | Yes | It's available in TAB "Payment Term" under the "Premium & Fees" page
29 | Commercial | Additional Details |  | Hide the TAB “Major Bank/Buyers” that exist under the "Transaction Details" page, for IXOL, IQTP policy types. |  | Change
30 | Commercial | NBI, Application and Policy |  | Under the section “Policy Details”, disable the calculation for fields "Policy Issuance Date" and “Policy Application Date”. |  | Change |  |  | Common
31 | Commercial | NBI, Application and Policy |  | Move the field "NBI Acceptance Date" to be in "Validity Details" section. |  | Change
32 | Declarations | Declaration Details |  | Move the “Invoice vs USD Rate Date” field beside the "Invoice Currency" field and rename it to “Invoice currency Exchange rate value Date” |  | Change
33 | Commercial | NBI, Application and Policy STP | STP | Two new fields "Shipment from date" & "Shipment to date". |  | Change
34 | Declarations | Declaration Details |  | Calculation for fields should not applied for saved data. (ex. Totals, Premiums, Ex. Rate, etc.) |  | Change |  |  | Common
35 | Declarations | Declaration Details/Reciept of payment |  | Rename the "Serial" to "Shipment No" |  | Change
36 | Declarations | Declaration Details/Reciept of payment |  | Add the Exchange rate (new field) beside the Currency field |  | Change
37 | Declarations | Declaration Details/Reciept of payment |  | "Total Payment Received so far" New field requested |  | Change
38 | Declarations | Declaration Details/Reciept of payment |  | New field request "Total (USD)" |  | Change
39 | OCL | OCL |  | Add the "Applicant name" to the field "Document Reference" in case the value is related to production stages (NBI, Application, Preliminary Application, Inquiry, Policy) |  | Change
40 | OCL | OCL |  | Document Reference is not retrieved when the field “Record Type” is equal to “CLA”, Ex. BNK-AL -00006 Version No 8 |  | Change
41 | OCL | OCL |  | ICIEC requested to remove the validation between column "Submission Reason" and "Sub-Reason" for saved data |  | Change |  |  | Common
42 | OCL | OCL |  | After search on certain OCL, and that OCL has more than one record in result and select one record from the search result, and then navigate to OCL details and after that when back to OCL main page, the search result just fetched the selected OCL. The requested to have always the first result that retrived. |  | Change
43 | OCL | OCL Details |  | Sub-Sector field is not retrieve value on the top page while its appeared in the main OCL page |  | Bug | Resolved | Yes
44 | OCL | OCL Details |  | The field "Current OCL" (that appears on the top when navigating to the OCL details page) is not available on the data migration sheet |  | Inquiry | Resolved | Yes | If the Limit Status is "Approved" it reads from the "Recommended Amount" otherwise it reads from the last approved version
45 | OCL | OCL Details / Recommendations |  | New field "Currency". |  | Change
46 | OCL | OCL Details / Recommendations |  | The field "Recommendation" has data migration and does not appear on the system. (same will be applied for submission reasons, etc.) |  | Change |  |  | Common
47 | Commercial | NBI, Application and Policy |  | Update the field source "Application Date" (That appeared on the top of the system page when navigating between pages) to "Registration Date" |  | Change
48 | Commercial | NBI, Application and Policy (STP) | STP | The new section requested "Capacity" |  | Change
49 | Commercial | NBI, Application and Policy (STP) | STP | A new field titled "Contract Type" has been requested, along with its details |  | Change
50 | Declarations | Declaration Details |  | Add two fields: “Our Retention %” and “Fronting Retention %” that will pull data from the policy page (Informative) |  | Change
51 | Commercial / Endorsements | Endorsements |  | New details for endorsement type "Group of companies" |  | Change
52 | Commercial | NBI, Application and Policy |  | Two new fields for Application "Offer validity" & "Offer Expiry Date" |  | Change
53 | Commercial | NBI, Application (STP) | STP | Display the “Applicant Details” (Application Experience) questions for the STP policy type |  | Change
54 | Commercial | Shipment and Repayment Schedule | STP | For the “Repayment Method”, if it is Bullet then the “Repayment Details” table should be hide |  | Change
55 | Commercial | NBI, Application and Policy (STP) | STP | New field "Effective Date of Contract" |  | Change
56 | Commercial / Fees | NBI, Application and Policy / Fees |  | When searching for the "Invoice Ref" the Fees page will only display data associated with that specific "Invoice Ref" |  | Change
57 | Commercial/Fees | Fees |  | Data does not appear for Sovereign, Ex. PP-UK -00119 Version No 1 |  | Bug | Resolved | Yes
58 | Commercial | Inward RI/ Treaty Detail/ Account Terms |  | Hide the below fields from the System Pages: *) "Overall Maximum Buyer Limit" *) "Overall Maximum Buyer Limit" *) "Overall Maximum Buyer Limit" |  | Change
59 | Commercial | Inward RI/ Treaty Detail/ Account Terms |  | Rename the below fields from the System Pages: *) "% of Premium Reserve Payable to WAQF" Rename to "% of Interest on Premium Reserve Released Payable to WAQF" *) "% of Claim Reserve Payable to WAQF" Rename to "% of Interest on Claim Reserve Released Payable to WAQF" *) "UW Adjust %" Rename to "Max. UW Year Adjustment % of Premium/Claim Reserve %" |  | Change
60 | Commercial | NBI, Application |  | Field “Basic Information”, the data not retrieved, Ex. NBI --> PP-AUA-00002 Version No 1, Application --> PP-AUA-00002 Version No 3 |  | Bug | Resolved | Yes
61 | Sovereign | Enquiry, Preliminary Application / Additional Details / Transaction Details |  | Check the source of the field "Total Transaction Amount" Under the "Additional Details" page, Ex. ENQ-AUA-00005, and rename based on the source | 2024-09-12 | Inquiry | Resolved | Yes | The source of the field is "Project Cost"
62 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Check the source of the field "Risk No. Discount" | 2024-09-12 | Inquiry | Resolved | Yes | The values are generated based on the count of Covers, if there are 2 covers then the value will be 10, and if it has 3 covers then the value will be 20, and if there are 4 covers then the value will be 25, otherwise the value will be 0
63 | Sovereign | Enquiry, Preliminary Application (Pricing document investment) |  | Check the source of the field "Policy Expiry Date", Ex. ENQ-AUA-00005 | 2024-09-12 | Change |  |  | There is no database field for "Policy Expiry Date"
64 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Check the TAB "Line Size" data with gray columns in the data migration sheet, Ex. ENQ-AUA-00005 Data remigrated | 2024-09-12 | Data Issue | Resolved | Yes
65 | Sovereign | Enquiry, PA, Ma, Policy and Renewal / Additional Details / Transaction Details |  | Update the field "Total cost of enterprise(Including debt and other Investor's contributions ,if any)" to be number not free text | 2024-09-12 | Change
66 | Sovereign | Enquiry, Preliminary Application (Pricing document investment) |  | Just for the migrated data, disable the calculation for the field "Amount of Cover" under the TAB "Additional Details" | 2024-09-12 | Change |  |  | Common
67 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Under the "Applicant Details" section, Change the label for fields ("Applicant Type" & "Applicant Name") to ("Invertor Type" & "Invertor Name") according to "Insurance Class"(Commercial or Sovereign) | 2024-09-12 | Change
68 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | The "Enterprise" is not available and the "Investor & Enterprise" that shall be on the main page of the Enquiry & PA | 2024-09-12 | Change
69 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Check and update the data for column AN "Master Document ID" Ex. ENQ-FR -00034 // Data Issue Reopened 12-12-2024 , Ex. : PP-FR -00079, Resolved 16-12-2024, Validated 17-12-2024 | 2024-09-12 | Data Issue | Resolved | Yes
70 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Search on the CLA for Sovereign | 2024-09-12 | Change
71 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Missing sheet "Eligibility Criteria" for "Premelinary Application" | 2024-09-12 | Data Issue | Resolved | Yes
72 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Under the "Cover Rates" page, display the "Standard Rates", Currently not appear for the migrated data | 2024-09-12 | Inquiry | Resolved | Yes | Its display the data that provided in "Sovereign" sheet under sheet "Cover Types Of Insurance Term" ICIEC Feedback: The feedback provided by ESKA is not valid because the page they are refer to related to policy data only not related to Enquiry, PA and MA
73 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Rename the TAB "Transaction Details" after discussing it in details with ICIEC | 2024-09-12 | Change
74 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Make sure that the list of reports that appear are based on the "Document Type" (Enquiry and Preliminary Application) | 2024-09-12 | Setup | Resolved | Yes | Unlink report from the setup Check and update the setup with ICIEC PA/MA Proforma Fee Invoice Proforma Invoice for Due Diligence Fee Letter of Registration Registration Expiry Notice FIIP Offer Letter To Applicant Issuance FII Policy Policy/Renewal FIIP Policy Schedule Policy Renewal Invitation Renewal Form Confirmation of Renewal Letter Confirming Lapse of Policy
75 | Sovereign / Report | Enquiry / CPD0068 |  | *) Subject should has the value of Point No. "3. Investment" *) Point No. "3. Investment", Should be the value of project description *) Point No. "6. Cover Required", Should list all covers *) Point No. "7. Amount of Cover", use the Currency name instead of Currency code *) Point No. "8. Max Liability Amount", To removed after checking the provided Template *) Point No. "9. Perc. (%) of cover", Add "%" beside the value *) Point No. "10. Premium Rate", Check the design and the Record label that exist in provided Template *) Point No. "11. Cover Period", Add "Years" beside the value *) Point No. "12. Fees", missing the values and to check the design from provided template, The first point i) is fixed, the second point the description is fixed and the value from the provided data *) Point No. 13. Other terms & Condition", To be read from field "Terms & Conditions" under Additional Details" TAB *) Check the fields border | 2024-09-12 | Bug | Resolved | Yes
76 | Commercial/Reports | CPD0013 (CSTP Non-Binding Indication (NBI)) |  | Check design and number formatting | 2024-09-12 | Bug | Resolved |  | Check the provided template from Drive-One folder PP-UAE-00316
77 | Commercial/Reports | CPD0315, SCHEDULE DOCUMENTARY CREDIT INSURANCE POLICY (DCIP) |  | “Business Activity Insured” column blank, Ex. PP-PAK-00074 PP-FR -00025 | 2024-09-12 | Bug | Resolved | Yes | Its read from Transaction Details/ Goods & Services/ Business Activity
78 | Commercial/Reports | CPD0319 Policy Schedule - Draft |  | Check design and number formatting | 2024-09-12 | Bug | Resolved | Yes
79 | Sovereign | Enquiry, Preliminary Application / "Additional Details" TAB (Policy Type : FIPE) |  | Check the source of field "Line Size" | 2024-12-12 | Inquiry | Resolved | Yes | Read from provided data from the data migration sheet "Pricing Document Investment" Column "Cover Amount" that exist under the sheet "Sovereign Production"
80 | All modules |  |  | Add a new field "Status" for the process in all modules(Commercial, Sovereign, Claims, etc.) | 2024-12-12 | Change |  |  | Common
81 | Sovereign | Enquiry (Policy Type : FIPE) |  | To show the Fees Amount value, the field is exist in Data migration sheet and in the data base. | 2024-12-12 | Change at No Extra Cost | Resolved | Yes | Check with ICIEC if it will appears for migrated data only
82 | Sovereign & Commercial | Enquiry, PA, MA, Policy and Renewal (Policy Type : FIPE) |  | The Status value "4 Policy Issued", this value not available in ESKA system, Ex. PP-FR -00079, The related column in the data migration sheet is "AQ" | 2024-12-12 | Data Issue | Resolved | Yes
83 | Sovereign | Preliminary Application/ Transaction details |  | Check the data for all fields under TAB "Transaction details", Ex. PP-FR -00079 Resolved 16-12-2024 | 2024-12-12 | Data Issue | Resolved | Yes | To check under "Economic Impact" TAB
84 | Sovereign | Preliminary Application/ sharholder |  | No data found under TAB "Shareholder", Ex. FIPF-UK -00010 Version No : 4 Resolved 16-12-2024 | 2024-12-12 | Data Issue | Resolved | Yes
85 | Sovereign | Preliminary Application |  | "Applied Amount" & "Recommended Amount" not exist, Screenshot attached | 2024-12-12 | Change
86 | Sovereign | Enquiry & Preliminary Application |  | The unit of the validaty for the Enquiry "In days", and for PA "In Months", and to calculate the expiry date accordingly | 2024-12-12 | Change | Canceled |  | Add new field for "Validity Unit" Cancelled Based on point No 184 (Rename the (Validity) to (Validity "In Days"))
87 | Sovereign | Enquiry |  | Hide the "Eligibility Creteria" for "Enquiry" | 17-12-2024 | Change at No Extra Cost | Resolved | Yes | Validated in CR verfication session on 20-01-2025
88 | Sovereign | Preliminary Application / Eligibility Creteria |  | The answers appears wrong, Ex. PP-AZ -00003 | 17-12-2024 | Change
89 | Sovereign | Preliminary Application / Additional details |  | Rename "Shareholding Category" To "Investment Type" for all Soverign policy types | 17-12-2024 | Change |  |  | .
90 | Sovereign | Preliminary Application / Additional details |  | Add one more Free text field "Description" | 17-12-2024 | Change
91 | Sovereign | (Main Application, Policy) / Additional details, Economic Impact |  | Hide the TAB "Shareholders", and check the data for MA that shall be available the same for the policy under the "Economic Impact" page | 17-12-2024 | Change at No Extra Cost | Resolved | Yes | Validated in CR verfication session on 20-01-2025
92 | Sovereign | Preliminary Application / "Additional Details" Page / Line Size TAB |  | Check the value for field "Commitment", Ex. PP-AZ -00003 ¦ wrong values displayed "Nan" | 17-12-2024 | Bug | Resolved | Yes
93 | Sovereign | Enquiry, Preliminary Application / "Additional Details" Page (Policy Type : FIPE) |  | Rename to "ICIEC Line Size" | 2024-12-12 | Change |  |  | .
94 | Sovereign | Preliminary Application, Main Application |  | 13 Missing sheets | 17-12-2024 | Missing Sheets | Resolved | Yes
95 | Claims | NPL |  | To have the versioning for NPL & Claims same the (NBI, Application, Enquiry, etc.) | 29-12-2024 | Change
96 | Claims | NPL |  | UW Recommendation has no data appears on the system page | 29-12-2024 | Bug | Resolved | Yes | Remove the validation for the value "4" of "Next Revision" 16-01-2025
97 | Claims | NPL |  | Read the Buyer & Ultimate Risk from approvals, This will apply just for current data, and for next migration the data will corrected, and the migration will read from provided data | 29-12-2024 | Data Issue | Resolved | Yes | Data correction
98 | Claims | NPL |  | Check the migrated data in the Declaration Tab, Ex. NPL-00477 - 1 Reopened Reason: The declaration has not appeared Reopened Sample: NPL-00058 - 2 (16-01-2025) CLM-00116 - 4 | 29-12-2024 | Bug | Resolved | Yes | The issue caused by the invoice currency for the declaration details is not equal the currency on NPL, the invoice currency has been updated to claim currency. Data correction Ex. NPL-00058 - 2 (16-01-2025)
99 | Claims | NPL |  | Under section "Buyer/Bank Info." Check the source of migrated data for columns: 1. Overall Credit Limit (USD) 2. Individual Credit Limit (USD) 3. Credit Period Example: NPL-00477 - 4 | 29-12-2024 | Inquiry | Resolved | Yes | 1. Overall Credit Limit (USD) OCL Recommendation, Recommended Amount 2. Individual Credit Limit (USD) Approval Premium, Approved ICL 3. Credit Period Approval Details, Total Credit Period
100 | Claims | NPL |  | Issue on the values for below columns from DM excel sheet: 1. Status, Column L 2. Stage, Column M 3. Recommendation, Column Z | 29-12-2024 | Note | Resolved | Yes | Under Review (Mentioned into CR Verification)
101 | Sovereign | Enquiry, Preliminary Application / "Additional Details" Page |  | New field "Line Size" | 29-12-2024 | Change
102 | Claims | Claims / Declaration "Invoices Details" TAB |  | In the claim declarations the field "Adjustment" does not display the minus values Reopened Reason: The declaration has not appeared Ex. CLM-00116 - 4 | 29-12-2024 | Bug | Resolved | Yes | Reopened 16-01-2025, and then Resolved in 18-01-2025
103 | Claims | Claims / Declaration "Invoices Details" TAB |  | In the claim declarations the Notes field is blank | 29-12-2024 | Data Issue | Resolved | Yes
104 | Claims | Claims / Declaration "Invoices Details" TAB |  | Check the data for column "Payment Before Claim (USD)", Ex. NPL-00477 - 4 | 29-12-2024 | Change |  |  | Reopened on 16-01-2025, and then Resolved in 18-01-2025 Reopened: The Declaration No displayed blank in the TAB "Invoice Details" The Approval status is cancelled that’s why the declaration is displayed blank.
105 | Claims | Claims |  | Check the source of data migration sheet "Payment Before Claims" | 29-12-2024 | Inquiry | Resolved | Yes
106 | CLA | CLA | IQTP | When tried to search on CLA 'IQA-00124' version No. 1, the data was not retrevied | 2025-01-05 | Data Issue | Resolved | Yes
107 | CLA | Scope of Cover |  | The data under the TAB Scope of Covers shall be the original sheet in Approvals sheet without include the risks from another sheet | 2025-01-05 | Change
108 | CLA | Scope of Cover | IQTP | Check where are the values for risks (Political, Commercial) without dates and location | 2025-01-05 | Inquiry | Resolved | Yes | Under Approval Pricing/ (TAB --> Premium Details)
109 | CLA | CLA | IQTP | The Application Status date not displayed, and it should add beside the Application Status, in the Sheet check the column G | 2025-01-05 | Change
110 | CLA | Security TAB | IQTP | The Guarantor Segment code not correct, Ex. IQA-00124/2 | 2025-01-05 | Data Issue | Resolved | Yes
111 | CLA | Approval Pricing | IQTP | Check the data source from which sheet for Limits. Ex.IQA-00124/2 To check the formula that get the data | 2025-01-05 | Inquiry | Resolved | Yes | CURRENT_OCL --> RECOMMENDED_AMOUNT_LC From Limit Recommendation Sheet ACTIVE_ICLS --> APPROVED_ICL_LC From Approval Premium Sheet TOTAL_ICLS_ISSUED --> APPROVED_ICL_LC From Approval Premium Sheet
112 | CLA | Approval Pricing/ Amount Details | IQTP | Check the value source for "Maximum ICL", Ex. IQA-00124/2 | 2025-01-05 | Change |  |  | Should read from the column in the data migration sheet is "W", Under the Approval premium sub-sheet Resolved reply: The value of "Maximum ICL" is retrevied from column ("F" MAX ICL) that exist in Sub-sheet "Recommendation" under the "OCL" sheet ICIEC Note: For the new casses its correct, but for the saved values it should be display as is.
113 | CLA | Other Conditions | IQTP | Make the TAB "Other Conditions" available for all policy types | 2025-08-01 | Change
114 | CLA | Approval Pricing /Amounts Details/ Share Distribution List | IQTP | Check the data that appeared on the system page, Ex. IQA-00124 version 3 | 2025-08-01 | Inquiry | Resolved | Yes
115 | CLA | Scope of Cover | IFRP,IQTP | The data for scope of cover shall be contain the data as provided, that’s will affect on claim declaration risk type | 2025-08-01 | Change
116 | CLA | CLA | IFRP | The policyholder not presented in the system page, the page is appeared the Reinsured | 2025-08-01 | Change
117 | CLA |  | IFRP | Check the data that provided in sheets("Approvals_IFRP-IQTP_Org Insur_Reinsured", "RI_INWARD") | 2025-09-01 | Data Issue | Resolved | Yes | Update the reinsured on CLA based on the sheet "Approvals_IFRP-IQTP_Org Insur_Reinsured"
118 | CLA | CLA | IFRP | Display the policy classification (Standard, Whole turn over) | 2025-09-01 | Change
119 | CLA |  | IFRP | Check the data that provided in the sheet "DM_RI_COMM_SHARE_DISTRB" | 2025-09-01 | Data Issue | Resolved | Yes | Need to check the source of Column "B" under sheet DM_RI_COMM_SHARE_DISTRB/RI COMM-APPLIED_CONTRACT AMOUNT
120 | CLA |  |  | Display the cancelation date Ex. APR-39857 | 2025-09-01 | Bug | Resolved | Yes
121 | CLA | Approval Pricing/ Premium Details | IFRP | Check the page design according to product type | 2025-09-01 | Change
122 | CLA | Approval Details / Goods & Sectors |  | Check the data for column "Risk Type" in sheet "Approval Details" Column "R" Ex. CRA-02856 Version No. 1 | 2025-09-01 | Bug | Resolved | Yes
123 | CLA | Amounts details | IFRP | Disable the calculation for amounts and exchange rate, Ex. CRA-01649 Version No 2 | 2025-09-01 | Change
124 | CLA | Payment Terms | IFRP | Disable the calculation for amounts, Ex. CRA-01649 Version No 2 | 2025-09-01 | Change
125 | CLA | Approval Pricing/ Premium Details | IFRP | In the data migration sheet under the sub sheet "Premium", the Country and Grade are not displayed on the system page | 2025-09-01 | Change at No Extra Cost | Resolved | Yes
126 | CLA | Inward RI | IFRP | Hide the TAB "Claim and Recoveries" | 2025-09-01 | Change |  |  | .
127 | CLA |  | IFRP | Update the above wizard by making the page "Approval Pricing" before the "Inward RI" | 2025-09-01 | Change at No Extra Cost | Resolved | Yes
128 | All modules |  |  | After duplicate the system page and back to the original system page the page clear the session | 2025-09-01 | Bug | Resolved | Yes | The system has been adjusted to clear the session if user navigates to a different module, even if in a separate browser
129 | Commercial |  | IFRP | Check and update the data that related to INWARD RI in "Commercial Production" Sheet, Coulmn in the sheet CB, CD,CE, CF | 2025-09-01 | Data Issue | Resolved | Yes | The value of "Ceding Commission %" & "ECA Retention" are wrong.
130 | CLA | Approval Pricing/ Premium Details | IFRP | disable the calculation for Premium Rate and to check and compare the values in the database with the provided data, Ex. CRA-02923 version 2 | 2025-12-01 | Change |  |  | Common point
131 | CLA | RI Inward/Original Details | IFRP, IQTP | Check the source of data for field "Approval Type" | 2025-12-01 | Inquiry | Resolved | Yes | Add a new point "248" to request data from ICIEC for the field "Approval Type"
132 | CLA |  | IFRP | Issue on search when selecting Credit Limit Application No, Ex. Credit Limit Application No., when using the Approval No. its retrieve the data | 13-01-2025 | Bug | Resolved | Yes
133 | CLA |  |  | Check the migrated data for field "Subsidiary", in the system its display blank DCA-01128 Version No. 1 | 13-01-2025 | Bug | Resolved | Yes | Failed Sample : DCA-00107
134 | CLA |  | IFRP | The Active flag appeared just when its active "CLA Is Active", if the CLA is not active need to mention that also, Ex. CRA-03221, Version 1 & 2 | 13-01-2025 | Change at No Extra Cost | Resolved | Yes
135 | CLA |  | IFRP | The column ("U" Source) in "Approvals" data migration sheet not displayed on the system page | 13-01-2025 | Bug | Resolved | Yes
136 | CLA | Approval details & Inward RI | IFRP | To hide the "Scope of Cover" exist under "Inward RI", and keep the Scope of cover that available under "Approval details" | 13-01-2025 | Change |  |  | .
137 | CLA | INWARD RI / Treaty Details | IFRP | Hide the option "Treaty Product Attachment" because there is no data and the Product Type already displayed on main page, for IFRP policy type | 13-01-2025 | Change
138 | CLA | INWARD RI / Other Retiention List | IFRP | Check the source of data for approvals, and check the country value, Ex. CRA-02758, version No. 6 | 13-01-2025 | Inquiry | Resolved | Yes | Compare the migrated data with the sheet "INWARD_RI". The country is generated from the country value in "Approval Details"
139 | CLA | INWARD RI / Treaty Details | IFRP | Check the "Details List" that exists under the "Treaty Terms and Conditions" (To check the data after checking the source of the system section "Details List") | 13-01-2025 | Inquiry | Resolved | Yes | Validation: Get the data based on the provided data in sheets "MAJOR_BUYERS” AND “IQTP_OTHER_RETENTION” for ("DOCUMENT ID" & "APPROVAL ID") ICIEC disagreed with the Validation, and there are two points added to the same subject
140 | CLA |  | IFRP | The pricing page shall be different based on "Policy Classification", if it Standard the premium shall be on approval level and to use the "Premium Schedule" | 13-01-2025 | Change
141 | CLA |  | IFRP | Check the column 'C" in Sheet : "DM_RI_COMM_SHARE_DISTRB" if it available on system or not | 13-01-2025 | Inquiry | Resolved | Yes | Column "C" is a "Commission %" if the "Whole Turnover policy" Or "Premium Discount %" if "Standard policy". Check the Report "Reinsurance Cover Note", CPD0535
142 | CLA | Payment Terms |  | The selection list doesn't appear e.g. CRA-00112 but it appears for others with the same policy type, e.g. CRA-00095 Version No 5 ICIEC reply: To determine who requested the validation mentioned above, remove it and display the data that was provided. Remove the validation for Migrated Data | 13-01-2025 | Change |  |  | In case the value of ("Line of Business" of the "Product Type") for the CLA In (2, 4) Then it will Appear Or If "Product Type" is Blank and "Line of Business" in (3,4) Then it will Appear. Below are the values of the "Line of Business": 1 --> Trade Credit Domestic 2 --> Trade Credit Export 3 --> Bank Export Financing 4 --> Bank Confirmation of LCs 5 --> Non-Honoring of Sovereign Financial Obligations 6 --> Foreign Investment 7 --> Single Transaction Trade Credit 8 --> Inward Reinsurance Below is the "Line of Business" Per "Policy Types": GAP --> Global Alliance Policy-Coface --> 2 CSTP --> Comprehensive Short Term Policy --> 2 SMTP --> Supplemental Medium Term Policy --> 2 DCR --> Credendo Policies --> 2 BMP --> Bank Master Policy --> 3 DCIP --> Documentary Credit Insurance Policy --> 4 STPCF --> Specific Transaction Policy - Contract Frustration --> 7 STP --> Specific Transaction Policy --> 7 IQTP --> Inward Quota Share Treaty Policy --> 8 IXOL --> Inward Excess Of Loss Policy --> 8 IFRPC --> Inward Facultative Reinsurance Policy - Contract --> 8 IFRP --> Inward Facultative Reinsurance Policy --> 8 IFRPI --> Inward Facultative Reinsurance Policy - INV --> 8 FIPF --> Foreign Investment Insurance Policy - Finance --> 4 FIPE --> Foreign Investment Insurance Policy - Equity --> 4 FIPL --> Foreign Investment Insurance Policy - Loan Guarantee --> 4 IFRP --> Inward Facultative Reinsurance Policy --> 8
143 | CLA |  | IFRP | Check where is the page for the sheet "Approval Installments" under Approvals Sheet Ex. CRA-00112 | 13-01-2025 | Inquiry | Resolved | Yes | Under the page "Approval Details"/"Payment Terms" for the approvals that have data for installments.
144 | CLA | Payment Terms |  | Check the validation for display and hide the fields, especially fields ("No. of Installments", "Interval (Days)","Grace Period", "Applicant internal limit on the bank", "Applicant indicative rate on conformation fee") ICIEC reply: To determine who requested the validation mentioned above, remove it and display the data that was provided. Remove the validation for Migrated Data | 14-01-2025 | Change |  |  | In case the value of ("Line of Business" of the "Product Type") for the CLA Not In (2, 3, 4) Then it will Appear Or If "Product Type" is Blank and "Line of Business" In (2) Then it will Appear. Below are the values of the "Line of Business": 1 --> Trade Credit Domestic 2 --> Trade Credit Export 3 --> Bank Export Financing 4 --> Bank Confirmation of LCs 5 --> Non-Honoring of Sovereign Financial Obligations 6 --> Foreign Investment 7 --> Single Transaction Trade Credit 8 --> Inward Reinsurance Below is the "Line of Business" Per "Policy Types": GAP --> Global Alliance Policy-Coface --> 2 CSTP --> Comprehensive Short Term Policy --> 2 SMTP --> Supplemental Medium Term Policy --> 2 DCR --> Credendo Policies --> 2 BMP --> Bank Master Policy --> 3 DCIP --> Documentary Credit Insurance Policy --> 4 STPCF --> Specific Transaction Policy - Contract Frustration --> 7 STP --> Specific Transaction Policy --> 7 IQTP --> Inward Quota Share Treaty Policy --> 8 IXOL --> Inward Excess Of Loss Policy --> 8 IFRPC --> Inward Facultative Reinsurance Policy - Contract --> 8 IFRP --> Inward Facultative Reinsurance Policy --> 8 IFRPI --> Inward Facultative Reinsurance Policy - INV --> 8 FIPF --> Foreign Investment Insurance Policy - Finance --> 4 FIPE --> Foreign Investment Insurance Policy - Equity --> 4 FIPL --> Foreign Investment Insurance Policy - Loan Guarantee --> 4 IFRP --> Inward Facultative Reinsurance Policy --> 8
145 | CLA |  |  | The value of "Product Type" is blank for some casses, Check and update values based on provided data, Ex. IQA-00483 | 14-01-2025 | Data Issue | Resolved | Yes
146 | CLA |  | BMP | Rename the label of field "Exporter" to "Policyholder" | 14-01-2025 | Change at No Extra Cost | Resolved | Yes
147 | CLA |  |  | Check and correct the Supplier value, Ex. FO -00526 Version No 1 | 14-01-2025 | Data Issue | Resolved | Yes
148 | CLA | Approval Details | BMP | Under the Security TAB, check and correct all values for Guarantor1 & Guarantor2 | 14-01-2025 | Data Issue | Resolved | Yes
149 | CLA | Approval Pricing | BMP | Under the "Amount Details" TAB, check and correct the values for field "Release" (R1, R2, R3). Ex. DCA-01206 , Version No. 11 | 14-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 22-01-2025
150 | CLA | Approval Summary / Security | BMP | The KYC Cleared value not the same one that appeared on the Approval Details/Security TAB, EX. FO -00526 | 14-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 22-01-2025
151 | CLA | Approval Summary / Experience With ICIEC |  | To check what is the data that shall be displayed Ex. CLA-04102 , Version No. 10 | 14-01-2025 | Note | Resolved | Yes | The data retrieved from OCL Recommendations Check the criteria that used to link the OCL with the CLA It retrieved the data based on the data that has a date less or equal to the approval effective date Ex. CLA-04102 , Version No. 10
152 | CLA | Approval Details / Payment Terms |  | Amount USD appeared blank, after the cursor on the Amount field and move out the field then the Amount USD calculate the value | 14-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 22-01-2025
153 | CLA | Approval Details, Approval Pricing, Approval Summary | BMP | After do refresh for the system pages the Inward RI page appeare, while it should not Available for BMP policy type. | 14-01-2025 | Bug | Resolved | Yes
154 | CLA | Approval Pricing / Amount Details |  | The value of the Exchange Rate is wrong, Ex. CSA-00157 | 14-01-2025 | Bug | Resolved | Yes
155 | CLA | Approval Pricing / Amount Details | BMP | Disable calculation for all fields, So that all the figures on the page will appear correctly basses on the provided data in the Data migration template | 14-01-2025 | Change
156 | CLA | Approval Pricing / Considerations / RPL |  | Minimize the width for "RPL Group","RPL Code" and increase the size of "Description" field | 15-01-2025 | Note | Resolved | Yes
157 | CLA | Approval Pricing / Considerations |  | Field "Considerations" can not increase the size, Add ability to increase the field size | 15-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 22-01-2025
158 | CLA | Approval Details / Goods & Sectors |  | Disable the calculation on saved data for fields "Policyholder & Buyer/Bank Located in Same Country","Buyer/Bank in a Free Zone with Policyholder’s Country" | 15-01-2025 | Change
159 | CLA | Approval Pricing / Premium Details |  | Field "ICIEC Standard Rate" shall has 4 decimal points | 15-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 22-01-2025
160 | CLA | Approval Pricing / Premium Details | DCIP DCR | Missing field "ICIEC Share" from data migration sheet | 15-01-2025 | Data Issue | Resolved | Yes
161 | CLA | Approval Summary / Goods & Sectors |  | The field "Percentage of Local Content" not display the value while its appear on the system page "Scope of cover", Ex. DCA-00772 Version No 4 | 15-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 22-01-2025
162 | CLA | Approval Summary / Security |  | The field "Guarantor 1 Country" & "Guarantor 2 Country" are display the value while there is no data on the system page "Security", Ex. DCA-00772 Version No 4 | 15-01-2025 | Bug | Resolved | Yes
163 | Follow Up History |  |  | Remigrate the data | 15-01-2025 | Data Issue | Resolved | Yes
164 | Claims | Claim Payable |  | Buyer value should be updated to view the Segment Code from Entity Roles instead of entity segment code | 16-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 23-01-2025
165 | NPL | Invoices Details |  | Check all details under TAB "Invoices Details" | 16-01-2025 | Inquiry | Resolved | Yes
166 | Commercial | NBI | STP | Hide the "Legal Status" TAB under "Additional Details" screen | 16-01-2025 | Change
167 | Commercial | NBI |  | Check the data migration into the sheet : "Eligibility-Shareholder Details" | 16-01-2025 | Data Issue | Resolved | Yes | To delete the duplicated records per each (NBI,App)
168 | Commercial | Transaction Details / Goods & Services | STP | The Below Fields not available: *) Origin of Goods Country *) Country of the Added Value | 16-01-2025 | Change |  |  | The page design is the same as CSTP
169 | Commercial | Transaction Details / Buyer | STP | The country appeared on the retrevied values but in Entry its appeared blank | 16-01-2025 | Bug | Resolved | Yes
170 | Commercial | Eligibility Creteria | STP | Rename the "Strategic Goods" to "Capital Goods" | 16-01-2025 | Bug | Resolved | Yes | Validated in CR verfication session on 20-01-2025
171 | Commercial | Insurance Terms | STP | The current system page design is for CSTP policy type, There is a screenshot from ICIEC system for "Insurance Terms" | 16-01-2025 | Change
172 | Commercial |  | STP | CLA is part of process(NBI, Application, Policy), The Details of CLA should be displayed on the (NBI,Application and Policy) | 19-01-2025 | Change
173 | Commercial | Pricing | STP | The Scope of cover should not be available. Premium not displayed in "Pricing Term", Ex. Application No "PP-TU -00088" | 19-01-2025 | Change at No Extra Cost | Resolved | Yes | Add the premium field to the summary page, under the "Premium Rate" section
174 | Commercial |  | STP | There is a missing section called "Capacity" | 19-01-2025 | Change
175 | Commercial | Shipment & Repayment | STP | Add the Exposure Curve "Dashboard" per each record("Shipment" Or "Repayment") | 19-01-2025 | Change |  |  | There is a screenshot
176 | Commercial | Application | STP | Rename "Offer Acceptance Date" to "Approval Effective Date" | 19-01-2025 | Change |  |  | .
177 | Commercial | Summary / Shipment/Execution Details | STP | The "Repayment" is not displayed on the page, just the "Shipment" data is displayed. E.g.: PP-BE -00005 Version No. 4 | 19-01-2025 | Bug | Resolved | Yes
178 | Commercial |  |  | Disable the validation for any posted case, for example, the Warning Message "Underwriting requirements are not completed!" that appears when navigating to the pricing page, e.g. Application No. "PP-TU -00088" | 19-01-2025 | Change at No Extra Cost | Resolved | Yes
179 | Commercial |  | STP | Check the source of value for field Master Policy, Ex. STP -TU -00003 Vesrion 6, 7 | 19-01-2025 | Inquiry | Resolved | Yes | Agreed to hide two fields "Policy Category","Master Policy"
180 | Commercial |  | STP | Hide the fields "Policy Category" & "Master Policy", STP business does not contain those fields. | 19-01-2025 | Change |  |  | .
181 | Commercial |  | STP | There is a missing section called ("Commitment" Ultimate risk ) which contain the obligor details, and (Applied Amount, Recommended Amount) | 20-01-2025 | Change
182 | Commercial | Policy | STP | Currently "Policy Issuance Date" is read "Issue Date" value from last Application, Should be read from the saved data in the data base from field "Issue Date", Ex. STP -SI -00011 | 20-01-2025 | Change at No Extra Cost | Resolved | Yes
183 | Commercial |  |  | Add the Latest policy status under the list of (NBI, Application and policy) and to display at once, and to replace the status in the Data list with the Recommendation | 22-01-2025 | Change
184 | Sovereign | PA, MA |  | Rename the "Validity" to "Validity in Days" | 22-01-2025 | Change |  |  | .
185 | Sovereign | Enquiry, PA |  | The section policy period details ("Policy From Date", "Policy Expiry Date") under "Policy Offer Details" section on main page should not be available for Enquiry & PA | 22-01-2025 | Change
186 | Sovereign |  |  | Rename the "Policy Period" to "Contract Period" | 22-01-2025 | Change |  |  | .
187 | Sovereign |  |  | Data is incorrect for below mentioned columns: In the Sovereign data migration sheet, columns(N,O and L) (Contract Period, Unit of Contract Period and Expiry Date) | 22-01-2025 | Data Issue | Resolved | Yes
188 | Sovereign |  |  | Hide the fields "Policy Category" & "Master Policy", Sovereign business does not contain those fields. Ex. PP-AUA-00003, PP-AZ -00003 | 22-01-2025 | Change |  |  | Same the "Point No. 180"
189 | Sovereign | Enquiry, PA, MA, Policy and Renewal |  | Rename the "Applicant Name" & "Applicant Type" to "Investor Name" & "Investor Type". Add the segment code for the policyholder "Investor Name" field under the "Applicant Details" section | 22-01-2025 | Change |  |  | .
190 | Sovereign | Enquiry, PA, MA, Policy and Renewal |  | Check if the the field "Sum Insured" available on the system page Ex. PA --> PP-AZ -00003 | 22-01-2025 | Change
191 | Sovereign | Agents TAB |  | Check the migrated data, Ex. ENQ-BE -00003 | 22-01-2025 | Data Issue | Resolved | Yes
192 | Sovereign | Eligibilty |  | The question “Is the Project Shariah Compatible?” Appears with the wrong answer. Ex. PP-FR -00069 Version No. 2 | 26-01-2025 | Change |  |  | Common
193 | Sovereign |  |  | Hide the TAB "Scope of Cover" under the "Additional Details/Insurance Details", And under the Summary page. Rename "Scope of Cover List" to "List of covered risks" that existing under "Cover Rates" page | 26-01-2025 | Change |  |  | .
194 | Sovereign | Additional Details |  | Copy all the data that provided for column "AD" under the sheet "Pricing Document Investment" to the "Special Conditions" | 26-01-2025 | Data Issue | Resolved | Yes
195 | Sovereign |  |  | Approval details is not shown in the system, Ex. PA : PP-GDR-00072 | 26-01-2025 | Change
196 | Sovereign | Economic Impact/Enterprise |  | Rename "Will the activity financed be new to the enterprise?" to "Will the activity financed by the investment be new to the enterprise?" | 26-01-2025 | Change |  |  | .
197 | Sovereign | MA/Pricing |  | Check and update the values for field "Percentage Of Cover" ,E.x PP-UK -00147 | 26-01-2025 | Data Issue | Resolved | Yes
198 | Sovereign | Pricing/ Loan Investment |  | Check the data under sheet "Pricing Document Investment" that provided under sheet "Sovereign Production_Additional PA-MA Data" | 26-01-2025 | Data Issue | Resolved | Yes
199 | Sovereign | Cover Rate |  | Check and update the data based on sheet "Sovereign Production_Additional PA-MA Data" | 26-01-2025 | Data Issue | Resolved | Yes
200 | Sovereign | Economic Impact / Project Viability |  | Check and update the data based on sheet "Sovereign Production_Additional PA-MA Data" | 26-01-2025 | Data Issue | Resolved | Yes
201 | Sovereign | Economic Impact |  | Labels of (fields, TABs etc.), shall be the same what in the application form | 26-01-2025 | Change
202 | Sovereign |  |  | Check the page on the system that related to sheet "Investment Experience" | 26-01-2025 | Inquiry | Resolved | Yes
203 | Sovereign | Economic Impact / Development Impact / "Investment Experience" |  | The migrated data does not appear on the system | 2025-01-27 | Bug | Resolved | Yes | There is aduplicated in details, Ex. PP-FR -00002
204 | Sovereign | Economic Impact /Relations/ General Info |  | Check and update the data based on sheet "Sovereign Production_Additional PA-MA Data" | 27-01-2025 | Data Issue | Resolved | Yes
205 | Sovereign | Economic Impact /Relations/ General Info |  | Check and update values for field "Investment Type", Ex. PP-UK -00147 version No. 3 | 2025-01-28 | Data Issue | Resolved | Yes
206 | Sovereign |  |  | To display the local amounts in all system pages in Sovereign, (For Example: MA stage, Segment Code: PP-TU -00169 Version No. 3) | 2025-01-28 | Change
207 | Sovereign | Pricing / Disbursements |  | Outstanding not displayed for Disbursments data | 2025-01-28 | Change
208 | Sovereign | Pricing / Disbursements |  | Check the field that has "Gross Premium" source, And what is the different between "Premium Amount Insured" and "Premium Amount Total" | 2025-01-28 | Inquiry | Resolved | Yes | Gross Premium not displayed, "Premium Amount Insured": Column V, From Sheet Sovereign Production_Additional PA-MA Data / Pricing Document "Premium Amount Total": Column Z, From Sheet Sovereign Production_Additional PA-MA Data / Pricing Document
209 | Sovereign | Pricing / Repayment |  | To show the "Cumulative Amount" on the system page | 2025-01-28 | Change
210 | Sovereign | Pricing / Repayment |  | The "Schedule" should be updated to be the same that displayed for the "Disbursements" | 28-01-2025 | Change | Canceled
211 | Sovereign | Enquiry, Preliminary Application (Policy Type : FIPE) |  | Under the "Cover Rates" page, To retrieve "Standard Rates", Currently for the migrated data does not appear. The page they are referred to related to policy data only, not related to Enquiry, PA and MA | 2025-01-28 | Change |  |  | Related to Point No 72
212 | Sovereign | Enquiry, PA & MA |  | Under section of "Policy Offer Details" Rename the below fields: *) "Policy Effective Date" to "Effective Date Of Contract" *) "Policy Contract Period" to "Contract Period" *) "Policy Expiry Date" to "Contract Expiry Date" | 2025-01-28 | Change |  |  | .
213 | Sovereign | Policy / MA |  | Check the source of the field "Expiry Date" under "Validity Details" section, and what that field means. Ex. FIPF-UK -00009 ICIEC: To remove any calculation for the migrated data | 2025-01-29 | Change |  |  | "Validity Details / Policy Expiry Date" --> Effective Date + Contract Period ICIEC: To remove any calculation for the migrated data
214 | Sovereign | Policy |  | Check the source of field "Issuance Date" under "Policy Details" section. Ex. FIPF-UK -00009 | 2025-01-29 | Inquiry | Resolved | Yes | The "Policy Issuance Date" is read as "Status Date" in the previous version "Policy Details / Policy From Date" --> Inception Date "Registration Date" --> Issue Date New point added, Point No. 251
215 | Sovereign | Policy |  | Signatory Details("Signatory", "Signatory Capacity" and "Signatory Date") are missing from the system page | 2025-01-29 | Inquiry | Resolved | Yes | Additional Details / Declaration & Applicant
216 | Sovereign | Policy, Renewal / Cover Rate |  | Based on data migration sheet, Most of the columns in the sheet "Cover Types Of Insurance Term" are missing from system page | 2025-01-29 | Change
217 | Sovereign | Policy, Renewal / Pricing /Loan Investment |  | The host country is missing, to check the sheet "Pricing Document Investment" in the column D | 2025-01-29 | Inquiry | Resolved | Yes | Additional Details / Transaction Details
218 | Sovereign | Policy , Renewal / Additional Details / Transaction Details |  | The "Project Cost" is not shown and to check the source of field "Total Cost" | 2025-01-29 | Inquiry | Resolved | Yes | Project Cost: Total Transaction Amount Total Cost: Total cost of enterprise(Including debt and other Investor's contributions ,if any)
219 | Sovereign | Pricing / Disbursements | FIPE | Hide this section for policy type "FIPE" | 2025-01-29 | Change
220 | Sovereign | Pricing |  | The field "Standby Rate" is not shown on the system page, under the sheet "Pricing Document Investment" | 2025-01-29 | Change
221 | Sovereign | Pricing |  | Rename the field "Premium Amount Stand By" to "Premium Amount Standby" | 2025-01-29 | Change |  |  | .
222 | Sovereign | Pricing |  | Check the source of "Standby Amount" and compare it with the sheet of "Pricing Document Investment" | 2025-01-29 | Inquiry | Resolved | Yes | Stand By Premium --> "Premium Amount Stand By"
223 | Sovereign | Enquiry, MA, Policy and Renewal / Cover Rates |  | Check the source of the field "Risk No. Discount" | 29-01-2025 | Data Issue | Resolved | Yes | The values are generated based on the count of Covers, if there are 2 covers then the value will be 10, and if it has 3 covers then the value will be 20, and if there are 4 covers then the value will be 25, otherwise the value will be 0
224 | Sovereign | Pricing/ Loan Investment |  | Check the data under sheet "Pricing Document Investment" and map sheet columns with system fields | 2025-01-29 | Inquiry | Resolved | Yes | Project Cost --> "Principal Amount " Cover Amount --> "Insured" Stand By Percentage --> "Not displayed on the system page" Insured Premium --> "Premium Amount Insured" Stand By Premium --> "Premium Amount Stand By" Total Premium --> "Not displayed on the system page"
225 | Claims | Invoices Details/Payment Before claim & Adjustment |  | Check the data for Notes field on "Payment Before Claim" & "Adjustment". | 2025-01-29 | Data Issue | Resolved | Yes
226 | Sovereign | Report / FIIP NBI Template |  | Rename the report "FIIP NBI Template" to "FIIP NBI" Ex. ENQ-BE -00010 | 2025-02-02 | Setup | Resolved | Yes
227 | Sovereign / Report | Report / FIIP NBI Template |  | For "Special Conditions" Update the data that migrated to be multi lines if it was provided multi lines Ex. ENQ-BE -00010 | 2025-02-02 | Bug | Resolved | Yes
228 | Sovereign | PA, MA / Summary |  | Replace the "Terms & Conditions" with "Special Conditions" | 2025-02-02 | Change |  |  | .
229 | Sovereign | Policy, Renewal / Special Condition |  | The data is migrated but its not appears on the system page. Ex. FIPF-GDR-00006 Version No 4 | 2025-02-02 | Bug | Resolved | Yes
230 | Claims | Claims / Invoice Details / Payment |  | To check the migrated data that contain symbols. Ex. NPL-00461 - 1 The Symbol :- € | 2025-02-02 | Database | Resolved | Yes | It's related to e "character set" of the Database
231 | Claims | Invoices Details/Payment Before claim & Adjustment |  | The Value of the "Final Amount"' is not the same that presented in the system page. (Disable the calculation) Ex. NPL-00460 - 7 | 2025-02-02 | Change
232 | Claims | Invoices Details/Payment Before claim & Adjustment |  | The Value of the "Loss Amount" that appears on the system page is wrong Ex. NPL-00460 - 7 CLM-00089 - 6 | 2025-02-02 | Change |  |  | Testing failed for Case CLM-00089 - 6 It gets the data from the production declaration details
233 | Follow Up History |  |  | Display the notes for each record, and the notes will display in section undernethed Ex. CLA --> CSA-00461 version 1 | 2025-02-03 | Bug | Resolved | Yes
234 | Follow Up History |  |  | Position is display the user code, while it should diplay the user position Ex. CLA --> CSA-00461 version 1 | 2025-02-03 | Bug | Resolved | Yes
235 | Follow Up History |  |  | Check the mapping between the user name that displayed with the provided data in the data migration sheet. Ex. CLA --> CSA-00461 version 1 | 2025-02-03 | Data Issue | Resolved | Yes
236 | Follow Up History |  |  | The users data date is incorrect for all records Ex. NBI --> PP-SAU-00296 | 2025-02-03 | Data Issue | Resolved | Yes
237 | Follow Up History |  |  | The action value is the same for all records, To check and update the values Ex. OCL --> BNK-AF -00001 | 2025-02-03 | Data Issue | Resolved | Yes
238 | Follow Up History |  |  | "Position To" is displayed blank for all records. | 2025-02-03 | Data Issue | Resolved | Yes
239 | Follow Up History |  |  | Check all migrated data, Ex. NPL-00371 Version No. 1 Ex. BNK-AGO-00001 Version 2 Ex. BYR-UAE-01654 Version 19 | 2025-02-03 | Data Issue | Resolved | Yes
240 | Follow Up History |  |  | The notes appear as one part while data has a multi line. Ex. BYR-UAE-01654 Version 21, Serial No. 11 | 2025-02-05 | Bug | Resolved | Yes
241 | Follow Up History |  |  | Check the Enquiry data, Ex. ENQ-AU -00001 | 2025-02-05 | Bug | Resolved | Yes
242 | CLA | Inward RI | IFRP IQTP | Hide the "Buyer's Details" that exist under "Inward RI" for CLA. | 2025-02-11 | Inquiry | Resolved | Yes | ICIEC Comment: Who asked to add the "Buyer's Details" under the "Inward RI" page The TAB "Buyer's Details" has been hidden
243 | CLA | INWARD RI / Treaty Details | IFRP | Who asked to add the validation mentioned in the Comment for point No. 139 | 2025-02-11 | Inquiry | Resolved |  | In reference to the notes captured from ICIEC on Points : 1.153 & 1.154 of CR2021 in the verification sheet, As below description: When Business Type = Inward at Policy,Application & NBI: FOR All Policy Types: 1- Remove multi select of product types from policy , application , & NBI. 2- Transaction Process Trail at Policy,Application & NBI for Inward business type to be replaced with Transaction Process Details for Direct Business . 3- Add New Process Trail : Inward RI , at Policy,Application & NBI for Inward business type. 4- When Policy type = IQTP then The New Transaction Process trail mentioned in point Number 2 must disappear. 5- AT CLA/Approval when Business type = Inward , show up the Inward RI Process mentioned above , while copying it's details from policy. those shall be editable incase of Standard , and Uneditable incase of wholeturn over. make sure that Pricing at The above documents and Approval is following the definition of the selected Product Type , with standard/Whole turnover , enable/disable validations.
244 | All modules |  |  | Disable the (Update, Save) for posted transactions. Ex. STP -BE -00001 Version No. 5, In the "Shipment & Repayment Schedule" page the Update button is enabled | 2025-02-11 | Bug | Resolved | Yes
245 | Sovereign / Report | Enquiry / CPD0068 |  | Check and update point No. 9 "Premium Rate" based on the provided template Remove the space between Point No. 11 & 12 | 2025-02-12 | Bug | Resolved | Yes
246 | CLA/ Reports | CLA / CPD0535 |  | Policy Reference is missing from the Report, and it should be the First Point. Report Name : "Reinsurance Cover Note" | 2025-02-12 | Bug | Resolved | Yes
247 | Sovereign | Enquiry, PA, MA, Policy & Renewal / Additional Details |  | Check the columns "J,N" "Project Cost, Cover Amount" from the ("Sovereign Sheet / Pricing Document Investment") sheet | 2025-02-12 | Inquiry | Canceled |  | Cover Amount --> Insured Project Cost --> Principal Amount Duplicated with Point No. 224
248 | CLA | RI Inward / Original Details |  | Migrate the data for field "Approval Type" | 2025-02-12 | Missing Sheets | Resolved | Yes | Approval Type - IFRP IQTP Transaction Type inside INWARD-RI Screen.xlsx
249 | Sovereign / Report | CPD0068 FIIP NBI | FIPE | Update the Cover Name from the setup for Cover "NHSO", to have the full name "Honoring of Sovereign Financial Obligation" Update the "Premium rate(s) per annum" to have the tenors e.g. Enquiry : ENQ-NE -00005 Version No. 3 | 2025-02-19 | Bug | Resolved | Yes
250 | CLA | Approval Summary / Experience With ICIEC |  | Rename the field "No. of NPLs" to "Total NPLs Amount" Rename "Total NPLS" to "No. of NPLs" Rename "Total of OS NPLS" to "Total of OS NPLs" Update the format for the count fields (No. of OS NPLS) & (Total NPLS) to be without decimal points Ex. CLA-04102, Version No. 10 | 2025-02-20 | Bug | Resolved | Yes | Make the field "No of Active Approvals" aligned to the right
251 | Sovereign | MA, Policy |  | Rename "Registration Date" to "Issue Date" | 2025-02-20 | Change
252 | Sovereign | Policy , Renewal / Additional Details / Transaction Details |  | Rename "Total Transaction Amount" to "Project Cost" | 2025-02-20 | Change
253 | Sovereign | Pricing/ Loan Investment |  | The value of "Premium Amount Insured", "Premium Amount Stand By", and "Premium Amount Total" are wrong, Ex. FIPE-CAI-00001 Version No. 10 | 2025-02-20 | Bug | Resolved | Yes
254 | Sovereign | Pricing/ Loan Investment |  | Add the below columns to the system page: * Standby Percentage * Total Premium | 2025-02-20 | Change
255 | OCL | OCL Summary / Experience With ICIEC |  | Rename the field "No. of NPLs" to "Total NPLs Amount" Rename "Total NPLS" to "No. of NPLs" Rename "Total of OS NPLS" to "Total of OS NPLs" Update the format for the count fields (No. of OS NPLS) & (Total NPLS) to be without decimal points Make the field "No of Active Approvals" alligment to right | 2025-03-02 | Bug | Resolved | Yes
256 | Customer Portal | Declaration |  | The “App Ref.” field is blank. The “Approved Amount” add amount format. The “Ex. Rate” “Shipment Date,” and “Final Rate” fields need to be wider. | 24-02-2025 | Bug | Resolved
257 | Customer Portal | CLA |  | The “Approved Amount” appeared with a “0” value, while there is an amount, regardless of the approval status. | 24-02-2025 | Bug | Resolved

## Reconciliation Progress (ESKA)
Credit Insurance Data Migration Reconciliation Status (From ESKADENIA's Perspective)
# | Area | Policy Types | Document Stage | Planned Status | Reconciliation Status | Total # of Sheets | # of Reconciled Sheets (Completed) | Remaining Sheets to be Reconciled | Reconciliation Progress % | Notes
1 | Countries |  |  | Done | Passed | 4 | 4 | 0 | 100%
2 | Entities |  |  | Done | Passed | 3 | 3 | 0 | 100%
3 | CIS |  |  | Done | Passed | 4 | 4 | 0 | 100%
4 | Credit Information Treaty |  |  | Done | Passed | 2 | 2 | 0 | 100%
5 | Fees | All |  | Done | Passed | 2 | 2 | 0 | 100%
6 | Endorsements | All |  | Done | Passed | 2 | 2 | 0 | 100%
7 | Portfolio Assignment | All |  | Done | Passed | 1 | 1 | 0 | 100%
8 | Commercial Production | CSTP |  | Done | Passed | 16 | 16 | 0 | 100%
|  | DCIP |  | Done | Passed | 16 | 16 | 0 | 100%
|  | BMB |  | Done | Passed | 16 | 16 | 0 | 100%
|  | GAP (Coface) |  | Done | Passed | 16 | 16 | 0 | 100%
|  | SMTP |  | Done | Passed | 16 | 16 | 0 | 100%
|  | DCR (Credendo) |  | Done | Passed | 16 | 16 | 0 | 100%
|  | STP |  | Done | Passed | 16 | 16 | 0 | 100%
|  | STP-CF | No Data Provided by ICIEC
|  | IFRP |  | Done | Passed | 16 | 16 | 0 | 100%
|  | IQTP |  | Done | Passed | 16 | 16 | 0 | 100%
|  | IXOL |  | Done | Passed | 16 | 16 | 0 | 100%
9 | Inward RI |  |  | Done | Passed | 27 | 27 | 0 | 100%
10 | OCL |  |  | Done | Passed | 4 | 4 | 0 | 100%
11 | Declarations |  |  | Done | Passed | 4 | 4 | 0 | 100%
12 | Sovereign Production | FIPE | Enquiry | Done | Passed | 3 | 3 | 0 | 100%
|  |  | Preliminary Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Main Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Policy & Renewal | Done | Passed | 17 | 17 | 0 | 100%
|  | FIPF | Enquiry | Done | Passed | 3 | 3 | 0 | 100%
|  |  | Preliminary Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Main Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Policy & Renewal | Done | Passed | 17 | 17 | 0 | 100%
|  | FIPL | Enquiry | Done | Passed | 3 | 3 | 0 | 100%
|  |  | Preliminary Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Main Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Policy & Renewal | Done | Passed | 17 | 17 | 0 | 100%
|  | FIPP | Enquiry | Done | Passed | 3 | 3 | 0 | 100%
|  |  | Preliminary Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Main Application | Done | Passed | 17 | 17 | 0 | 100%
|  |  | Policy & Renewal | Done | Passed | 17 | 17 | 0 | 100%
13 | CLA | IQTP |  | Done | Passed | 11 | 11 | 0 | 100%
|  | IFRP |  | Done | Failed | 11 | 10 | 1 | 90.91% | One Bug Point (Following the outcome of the Inquiry)
|  | CSTP |  | Done | Passed | 8 | 8 | 0 | 100%
|  | DCIP |  | Done | Passed | 8 | 8 | 0 | 100%
|  | BMB |  | Done | Passed | 8 | 8 | 0 | 100%
|  | GAP (Coface) |  | Done | Passed | 8 | 8 | 0 | 100%
|  | SMTP | Not Available
|  | DCR (Credendo) |  | Done | Passed | 8 | 8 | 0 | 100%
|  | STP | Not Available
|  | STP-CF | Not Available
|  | IXOL | Not Available
14 | Claims |  |  | Done | Passed | 6 | 6 | 0 | 100%
15 | Production Re-Insurance |  |  | Done | Failed | 2 | 1 | 1 | 50% | *) There is a pending point, based on the Discussion between Br Das & Ruba *) Migration in-progress
16 | Claims Re-Insurance |  | No Data Provided by ICIEC
17 | Followup History |  |  | Done | Passed | 4 | 4 | 0 | 100%
18 | CP Users |  |  | Done | Passed | 2 | 2 | 0 | 100% | Design Issues

## Reconciliation Progress (ICIEC)
Credit Insurance Data Migration Reconciliation Status (From ESKADENIA's Perspective)
# | Area | Policy Types | Document Stage | Planned Status | Reconciliation Status | Total # of Sheets | # of Reconciled Sheets (Completed) | Remaining Sheets to be Reconciled | Reconciliation Progress % | Notes
1 | Countries |  |  | Done | Passed | 4 | 4 | 0 | 100%
2 | Entities |  |  | Done | Passed | 3 | 3 | 0 | 100%
3 | CIS |  |  | Done | Passed | 4 | 4 | 0 | 100%
4 | Credit Information Treaty |  |  | Done | Passed | 2 | 2 | 0 | 100%
5 | Fees | All |  | Done | Failed | 2 | 1 | 1 | 50% | New points requested
6 | Endorsements | All |  | Done | Failed | 2 | 1 | 1 | 50% | New points requested
7 | Portfolio Assignment | All |  | Done | Failed | 1 | 0 | 1 | 0% | New points requested
8 | Commercial Production | CSTP |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | DCIP |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | BMB |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | GAP (Coface) |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | SMTP |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | DCR (Credendo) |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | STP |  | Done | Failed | 16 | 14 | 2 | 87.5% | New points requested
|  | STP-CF | No Data Provided by ICIEC
|  | IFRP |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | IQTP |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
|  | IXOL |  | Done | Failed | 16 | 15 | 1 | 93.75% | New points requested
9 | Inward RI |  |  | Done | Passed | 27 | 27 | 0 | 100%
10 | OCL |  |  | Done | Failed | 4 | 2 | 2 | 50% | New points requested
11 | Declarations |  |  | Done | Failed | 4 | 3 | 1 | 75% | New points requested
12 | Sovereign Production | FIPE | Enquiry | Done | Failed | 3 | 2 | 1 | 66.67% | New points requested
|  |  | Preliminary Application | Done | Failed | 17 | 15 | 2 | 88.24% | New points requested
|  |  | Main Application | Done | Failed | 17 | 15 | 2 | 88.24% | New points requested
|  |  | Policy & Renewal | Done | Failed | 17 | 15 | 2 | 88.24% | New points requested
|  | FIPF | Enquiry | Done | Failed | 3 | 2 | 1 | 66.67% | New points requested
|  |  | Preliminary Application | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  |  | Main Application | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  |  | Policy & Renewal | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  | FIPL | Enquiry | Done | Failed | 3 | 2 | 1 | 66.67% | New points requested
|  |  | Preliminary Application | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  |  | Main Application | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  |  | Policy & Renewal | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  | FIPP | Enquiry | Done | Failed | 3 | 2 | 1 | 66.67% | New points requested
|  |  | Preliminary Application | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  |  | Main Application | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
|  |  | Policy & Renewal | Done | Failed | 17 | 16 | 1 | 94.12% | New points requested
13 | CLA | IQTP |  | Done | Failed | 11 | 7 | 4 | 63.64% | New points requested
|  | IFRP |  | Done | Failed | 11 | 10 | 1 | 90.91% | One Bug Point (Following the outcome of the Inquiry)
|  | CSTP |  | Done | Failed | 8 | 7 | 1 | 87.5% | New points requested
|  | DCIP |  | Done | Failed | 8 | 7 | 1 | 87.5% | New points requested
|  | BMB |  | Done | Failed | 8 | 6 | 2 | 75% | New points requested
|  | GAP (Coface) |  | Done | Failed | 8 | 7 | 1 | 87.5% | New points requested
|  | SMTP | Not Available
|  | DCR (Credendo) |  | Done | Passed | 8 | 8 | 0 | 100%
|  | STP | Not Available
|  | STP-CF | Not Available
|  | IXOL | Not Available
14 | Claims |  |  | Done | Failed | 6 | 5 | 1 | 83.33% | New points requested
15 | Production Re-Insurance |  |  | Done | Failed | 2 | 1 | 1 | 50% | There is a pending point, based on the Discussion between Br Das & Ruba
16 | Claims Re-Insurance |  | No Data Provided by ICIEC
17 | Followup History |  |  | Done | Passed | 4 | 4 | 0 | 100%
18 | CP Users |  |  | Done | Passed | 2 | 2 | 0 | 100% | Design issues

## Migration Reconciliation Plan
# | Topic | 2024-10-20 |  |  |  |  | 2024-10-27 |  |  |  |  | 2024-11-03 |  |  |  |  | 2024-11-10 |  |  |  |  | 2024-11-17 |  |  |  |  | 2024-11-24 |  |  |  |  | 2024-12-01 |  |  |  |  | 2024-12-08 |  |  |  |  | 2024-12-15 |  |  |  |  | 2024-12-22 |  |  |  |  | 2024-12-29 |  |  |  |  | 2025-01-06 |  |  |  |  | 2025-01-13
|  | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17
1 | Entities
2 | Countries | [14 empty] | *
3 | CIS | [14 empty] | *
4 | Credit Info Treaties | [14 empty] | *
5 | Commercial Production |  |  | * | * | * |  | * | * | * | * | * | * | * | * | * | * | * | * | * | *
| Fees (separated based on Reyaz Request) | [16 empty] | * | *
| Endorsement (separated based on Reyaz Request) | [8 empty] | * | [25 empty] | *
| Inward RI (separated based on Reyaz Request) | [20 empty] | * | *
| Portfolio Assignment (separated based on Reyaz Request) |  |  |  | *
OCL (separated based on Reyaz Request)
6 | Declarations | [25 empty] | * | * | *
7 | CLA Application Approval | [30 empty] | * | * | *
8 | Sovereign Production | [35 empty] | * | * | * | * | * | * | *
9 | Claims | [47 empty] | * | * | *
10 | Credit DM - RI Production | [53 empty] | * | * | * | *
11 | ICIEC CP Users | [60 empty] | * | *
|  | * | Reconciliation Activity with ICIEC
Buffer time; Data Correction & Issues Resolution
Under section of "Policy Offer Details" Rename the below fields: *) "Policy Effective Date" to "Effective Date Of Contract" *) "Policy Contract Period" to "Contract Period" *) "Policy Expiry Date" to "Contract Expiry Date"