## Slide 1
ICIEC
ESKADENIA’s Remarks Justification Basis

## Slide 2: Summary
ESKADENIA’s Position Basis
What is a Change
Accomplished Milestones & Project Turning Points
Project Current Status

## Slide 3: ESKADENIA’s Position Basis
The Approved & Signed Scope Documents
  - BRD (Business Requirements Documents)
  Business Processes
  Signed CRs (2020, 2021, 2022 & 2024)
Appendix A to the Master Agreement – Section 3 Data Lifecycle Management (Actions by ICIEC)
“Data cleansing: This consists of:
  Purging the obsolete data based on rules to be defined,
  Correcting the data in the existing System(s),
  Completing the missing data in the existing System(s),
  Archiving the data, if need be based on rules to be defined”
Appendix A to the Master Agreement – Section 7 Scope Change Requests
  “Management of scope needs to be strictly enforced. All project team members should ensure that they are familiar with the scope and ensure that the design and deliverables remain within the boundaries of this scope.”

## Slide 4: What is a Change
Any Additional Required Professional Services
- System Customization; Additions, Adjustments, Alterations, or Deletions
(Functionalities, Features, Enhancements, UI/UX, Reports, etc.)
  Setup Re-configuration/ Configuration
  Extended Training Activities
  Extended UAT Activities
  Integrations with 3rd Parties
  Extended Data Migration
  Discussions & Assessments of New Requests

## Slide 5: Accomplished Milestones & Project Turning Points
Project Charter
Acceptance
CR 01_2020
  CR 01_2020 Scope Sign-off
Provisional Acceptance
  Acceptance of System Installation of all solutions in scope.
Apr 2019
Jun 2020
Jul 2020
Original Scope Definition & Approval
  Credit Insurance BRD & business Processes
  Customer Portal, Agent Portal & Banc-assurance BRDs & Business Processes Documents
  Financial System Gap Scope Document & Business Processes
  Financial Integration Scope Document
  CRM Gap Scope Document & Business Processes
Dec 2019 – Feb 2020
Requirements Gathering &
Gap Analysis
Original Scope Verification
CR 01_2020 Partial Verification
Training & Knowledge Transfer Sessions
CR 01_2020 Partial Verification
Covid 19 Pandemic

## Slide 6: Accomplished Milestones & Project Turning Points
Training Acceptance
  Delivery and Acceptance of Training of all solutions in scope.
CR 01_2024
  CR 01_2024
  Scope Sign-off
Dec 2021
Feb 2024
CR 01_2022
  CR 01_2022
  Scope Sign-off
Jun 2022
CR 01_2021
  CR 01_2021
  Scope Sign-off
Mar/ Apr 2021
Training & Knowledge Transfer Sessions
Training log sheet assessment
CR 01_2021 Partial Verification
CR 01_2022 Partial Verification
UAT Sessions
UAT Sessions
CRs & Data Reconciliation Remarks Assessment (New Points)
All CRs Verification & Re-verification
Covid 19 Pandemic

## Slide 7: Project Current Status
CRs & Data Reconciliation Remarks Assessment (New Points)
CRs Verification
Data Reconciliation
The CRs verification is completed from ESKADENIA’s Perspective
ESKADENIA has shared the justification on why the list of Remarks (which needs development) are out of the scope
ICIEC has shared the feedback on why the list of Remarks (which needs development) are within the scope
The data reconciliation is completed from ESKADENIA’s Perspective
ESKADENIA has shared the justification on why the list of Remarks (which needs development) are out of the scope
ICIEC has shared the feedback on why the list of Remarks (which needs development) are within of the scope
  P.S. As per the feedback received from ICIEC on the 13th of Jan, 2025; ICIEC will not proceed with the training and UAT activities unless the requested points raised under activities (the CRs verification and especially the data reconciliation) are developed and delivered.

## Slide 8: Thank You
www.eskadenia.com