Minutes of Meeting

| Date |  | 07.04.2019 |
| --- | --- | --- |
| Time |  | 09:00 am – 11:00 am |
| Venue |  | ICIEC – Building #3 |
| Subject |  | ICIEC Project ¦ Kick-off Meeting |
| Contact | Name | Laisan Mobaideen |
|  | Email | l.mobaideen@eskadenia.com |

Attendees

| Company | Attendee | Title |
| --- | --- | --- |
| ICIEC | Mr. Mohamud Khalif | Acting CEO and Acting Director Underwriting / Manager Insurance Operations, Sovereign Risks |
| ICIEC | Mr. Mohamad El Sayed | Finance & IT / Manager IT, Project Manager |
| ICIEC | Mr. Ahmed Arbee | Finance & IT / Finance – Acting Director |
| ICIEC | Mr. Reyaz Ahmed Wani | Finance & IT / IT |
| ICIEC | Mr. Suleiman Abutayeh | Finance & IT / Manager Finance |
| ICIEC | Mr. Dhirendra Kumar Das | Finance & IT / IT |
| ICIEC | Mr. Irfan Arshad Arshad | Business Development / ASIA Region |
| ICIEC | Mr. Rony Azar | Business Development / ASIA Region |
| ICIEC | Ms. Sabah Al - Harbi | Business Development / MENA Region |
| ICIEC | Mr. Bessem Soua | Business Development / Manager SSAE Region |
| ICIEC | Mr. Oguz Aktuna | Business Development / SSAE Region |
| ICIEC | Mr. Salih Suwarelzahab | Legal / Claims & Recovery |
| ICIEC | Mr. Mohd Ferdaus Mohd Khasim | Re-Insurance |
| ICIEC | Mr. Lotfi Zairi | Risk Management - Manager |
| ICIEC | Mr. Tauhidur Rahman | Risk Management |
| ICIEC | Mr. Faisal Bahmaid | Underwriting /Insurance Operations, Commercial Risks |
| ICIEC | Mr. Haitham Rehaimi | Underwriting /Insurance Operations, Commercial Risks |
| ICIEC | Mr. Shoaib Nawaz | Underwriting /Insurance Operations, Commercial Risks |
| ICIEC | Ms. Teif Aldoairem | Underwriting /Insurance Operations, Commercial Risks |
| ICIEC | Mr. Wael Makki | Underwriting /Insurance Operations, Commercial Risks |
| ICIEC | Mr. Bakari Kolley | Underwriting / Insurance Operations, Sovereign Risks |
| ICIEC | Mr. Moataz Zawam | Underwriting / Insurance Operations, Sovereign Risks |
| ICIEC | Mr. Raphael Fofana | Underwriting / Insurance Operations, Sovereign Risks |
| ICIEC | Mr. Hussain Alseid Omar | Underwriting / Support Manager |
| ESKADENIA | Ms. Laisan Mobaideen | Project Manager |
| ESKADENIA | Mr. Mohammad Amoudi | Insurance Business Unit Manager |
| ESKADENIA | Mr. Radwan Al-Jundi | Credit Product Manager |

## Objective

- Officially announce the project is underway.

- Showcase the project lifecycle and the expectations per each phase.

- Review the updated project charter | with Mohamad El-Sayed

- Review the project schedule | with Mohamad El-Sayed

# Minutes of meeting

- Welcoming note by Mr. Mohamad El-Sayed introducing the teams from both ICIEC & ESKADENIA sides.

- ESKADENIA PM along with Mr. Mohamad El-Sayed emphasized the importance of this project as being part of ICIEC’s digital transformation strategic objective which needs efficient collaboration & coordination between both parties.

- Showcase the project schedule, phases, deliverables and activities.

- Showcase the project key milestones.

- Share the on-site visit schedule & the agenda for the 1st two weeks of requirements gathering & gap analysis sessions.

- High-level discussion of the updated project charter with Mr. Mohamad Al-Sayed.

- Discuss the Project Risks with Mr. Mohamad El-Sayed:

| Risks | Impact | Preventive Action |
| --- | --- | --- |
| Delay in reaching a final/ consolidated gap scope document agreed by ICIEC team which will impact the development and delivery phase, because the number of members from ICIEC side who will provide the requirements is high and each might provide the gap as per his/ her own perspective | High | * To have a representative ¦ key business owner ¦ from each ICIEC department to provide one consolidated document that presents the needed requirements. * Each representative from ICIEC to coordinate internally with the remaining business users in order to set the needed requirements * ESKADENIA will suggest the best process practices based on its experience in the Insurance Industry |
| Changing on the approved gap scope documents | High | * Changes to the scope - not covered under the SoW - be implemented in CR orders post going live |
| Delay in issuing KSA invitation letters for ESKA resources which might impact the project on-site activities. Delay in issuing KSA visa for ESKADENIA employees. Master Agreement 10.4 “ESKADENIA will be fully responsible for obtaining visas for entry to and exit from the Kingdom of Saudi Arabia for the Personnel, and where applicable for their dependents, and such licenses and permits as may be necessary. Nevertheless, ICIEC shall, upon request by ESKADENIA, provide all reasonable assistance and support to facilitate obtaining of such visas and permits” | High | - Prepare for the onsite activities ahead. - Find alternatives for the resources (from both sides)/ or if the activities can be done offsite. - Keep the other party informed with the progress of issuing the invitation letters & the visa’s. |
| Delay in getting ICIEC setup & migration data ready | High | * Full cooperation from ICIEC side in terms of providing the setup data required for running the systems. |
| Not be able to meet the project Go-Live announcement date per each phase. | High | * Proper allocation of resources from both parties. * Full cooperation between ICIEC & ESKADENIA * Based on the actual effort estimate needed to deliver the gap per system, the impact on the schedule must be communicated and agreed between both parties |
| ICIEC key resource/ key player leaving the project without handing over the activities to another resource and without informing ESKA with the change might impact the activities due dates. | Medium | * Managing and monitoring the resources assigned to the projects. * Keep the resources aware ahead of time of the project activities agreed between both parties. * Keep the other party informed and aware ahead of the resource change |

- Lessons learned from previous projects:

- To keep all parties notified with the changing on the plan from both sides and to prepare for the onsite visits ahead.

- ESKADENIA recommends having one key ICIEC representative from each line of business to have the communication with ICIEC & requirements definition more focused and clear and to avoid scope creep.

- The project charter was signed by Mr. Mohammad El-Sayed on 11.04.2019.